## Cover
LUMENALIS CONSULTING LTD. — SAMPLE DELIVERABLE
CUSTOM SINGLE-DETACHED RESIDENCE (ELEVATOR-EQUIPPED) — CONSTRUCTION BUDGET
PRELIMINARY ¦ AACE Class 3 ¦ Pre-Tender ¦ Anonymised sample
PROJECT IDENTIFICATION
Project | Custom single-detached residence — owner-occupied
Location | Established residential neighbourhood, Ottawa, Ontario (address withheld)
Client | Withheld — private owner
Advisory role | Construction manager on cost-plus / construction-management engagement
Architect | Project architect (identity withheld); stamped For-Permit set
Structural engineer | Engaged for foundation, framing, elevator and steel (identity withheld)
Permit set status | Stamped For Permit (Rev 1)
Estimate prepared by | Development Project Manager (OAA Intern Architect)
Estimate classification | AACE International RP 18R-97 — Class 3 ( -10% to -20% / +10% to +30% )
Source documents | Stamped permit set; first-pass internal budget (audited & rebuilt — see QA_Checks); owner-confirmed allowances; window-supplier pricing relationship; Altus 2024-25 Canadian Cost Guide Ottawa CMA; BTY Q4-2025 Ontario residential infill; OBC O.Reg 332/12 SB-12; City of Ottawa By-law 2014-149
Status | PRELIMINARY — FOR DISCUSSION ONLY — NOT FOR TENDER OR CONTRACT
HEADLINE BUDGET OUTPUTS (linked from Summary)
Base hard construction costs (firm scope)
Soft costs (owner-paid / pass-through)
Owner-directed selections — low / high range
Owner-directed selections — high-end ceiling
Construction-management fee — 16% of base hard costs
Construction contingency — 10% of base hard costs (owner-held)
TOTAL PROJECT COST — pre-HST, base case
Embedded HST estimate (13%) — base case
TOTAL PROJECT COST — incl. embedded HST, base case
Habitable GBA (sq. ft.)
Base hard cost per sq. ft. habitable
Total project cost (incl HST) per sq. ft. — base case
DISCLAIMER
This is an anonymised sample derived from a real preliminary AACE Class 3 construction budget prepared for pre-contract discussion with a private owner. It is not a fixed price, not a tender package, and not a contract document. All client, address, consultant, and supplier identifiers have been removed under the Personal Information Protection and Electronic Documents Act (S.C. 2000, c.5); dollar figures are preserved. Final construction cost depends on competitive trade tendering, municipal permit comments, structural and mechanical coordination, geotechnical findings, owner finish selections, schedule, and market conditions at procurement. Values flagged ASSUMED or BENCHMARKED are subject to confirmation. Refer to Assumptions, Sources_Method, and QA_Checks for the audit trail.

## Summary
CUSTOM SINGLE-DETACHED RESIDENCE (ELEVATOR-EQUIPPED) — BUDGET SUMMARY
Two cost streams: a firm base hard cost the construction manager procures and manages, and an owner-directed selections budget the owner controls. All values are linked formulas; edit drivers on the Assumptions tab.
Cost category | Amount (CAD) | % of base-case TPC | Notes
HARD & SOFT COSTS
Base hard construction costs (firm scope — CM-managed) |  |  | From Hard_Costs grand total (includes the $100,000 unallocated allowance); owner-directed selections excluded.
Soft costs (design, engineering, permits, development charges, insurance, legal) |  |  | Owner-paid / pass-through. Largely HST-exempt municipal levies plus taxable professional services.
OWNER-DIRECTED SELECTIONS
Selections — low-end allowance (carried in base case) |  |  | Premium-custom allowance carried in the base-case total below.
Selections — high-end ceiling (defensible) |  |  | Most expensive defensible spec within design intent; above this = written change order.
FEE & CONTINGENCY
Construction-management fee — 16% of base hard costs |  |  | Lump-sum commitment; reconciled at substantial completion to approved hard costs and selections.
Construction contingency — 10% of base hard costs (owner-held) |  |  | Owner-held; drawn only on signed change order. The client-facing proposal folds this into the AACE band, the selections range, and the change-order process rather than showing it as a line; it is retained here as an internal-rigour item.
TOTAL PROJECT COST — PRE-HST
Base case — selections at low-end allowance |  |  | Base hard + soft + selections (low) + fee + contingency. Excludes HST (below).
High case — selections at ceiling; fee on +10% hard-cost variance |  |  | Owner-planning bracket.
HST TREATMENT — OWNER-OCCUPIED CUSTOM HOME
Embedded HST (13%) — base case |  |  | 13% on taxable construction (base hard + selections low) plus the CM fee. Owner-occupied custom build: HST is an embedded cost — no input-tax-credit recovery. Government levies and development charges within soft costs are largely HST-exempt and excluded here; taxable professional services within soft costs are owner-paid. Confirm Ontario New Housing Rebate eligibility ($24,000 max) with a tax advisor.
TOTAL PROJECT COST INCL. EMBEDDED HST — base case |  |  | Final base-case figure: pre-HST base-case TPC plus embedded HST.
Memo: TPC incl. embedded HST — high case |  |  | High-case bracket for owner planning.
KEY METRICS
Habitable gross building area (sq. ft.) |  |  | Basement + main + second; excludes integrated garage.
Base hard cost per sq. ft. — habitable |  |  | Firm scope only; excludes owner selections.
Total construction per sq. ft. — base case (base hard + selections low)
Total construction per sq. ft. — high case (base hard + selections high)
Ottawa premium-custom hard-cost benchmark — $/sf habitable |  |  | Altus Group Canadian Cost Guide 2024/25, Ottawa CMA.
Base hard cost variance vs benchmark — $/sf |  |  | Negative = below benchmark. Owner selections drive the all-in toward and above benchmark.
Soft cost as % of total construction (base hard + selections low) |  |  | Typical Ottawa premium custom 9-14%.
Base-case TPC incl. HST per sq. ft. — habitable

## Assumptions
CUSTOM SINGLE-DETACHED RESIDENCE (ELEVATOR-EQUIPPED) — ASSUMPTIONS
All blue cells are editable inputs. Every cost on Hard_Costs / Soft_Costs ties to one of these driver cells.
Driver | Value | Source / basis (academic, industry, or regulatory)
PROGRAM — FLOOR AREAS (basis: the architect's project file stamped permit set, 01-05-2026)
Basement habitable area — interior, sq. ft. | 1320 | Sheet A-005 stamped plan annotation: '1320 ft² Interior Space'
Integrated garage — interior, sq. ft. | 460 | Sheet A-005 stamped plan annotation: '460ft²'
Main floor habitable — interior, sq. ft. | 1475 | Sheet A-006: '1475ft² Floor space / 1820ft² total space' — 1,475 is interior habitable; 1,820 includes garage span
Second floor habitable — interior, sq. ft. | 1840 | Sheet A-007 stamped plan annotation: '1840 ft² Interior Space'
Rooftop patio — accessible deck area, sq. ft. | 280 | ASSUMED — Sheet A-204 roof plan, accessible portion under composite decking on pedestals; confirm with architect takeoff
Habitable GBA (excl. garage) — sq. ft. |  | Computed: basement + main + second
Total GBA (incl. garage) — sq. ft. |  | Computed: habitable + garage
EXTERIOR ENVELOPE — CLADDING AREAS (basis: architect sheet A-002 Wall Types W1/W2/W3 + elevations A-300/A-301)
W1 stone masonry — area, sq. ft. (front facade only) | 320 | ASSUMED — elevation takeoff from A-300/A-300a; corrects v2 first-pass which used 850 sf without basis. Verify with the architect
W2 aluminum wood-look paneling — area, sq. ft. (front facade) | 280 | ASSUMED — A-300 front elevation panel zones; verify with architect quantity-surveyor takeoff
W3 stucco (Adex-RS or equivalent) — area, sq. ft. (sides + rear) | 2300 | ASSUMED — A-300a / A-300b / A-301; sides + rear elevations exclusive of window/door openings; verify with takeoff
WINDOWS & DOORS (basis: architect sheet A-003 Window and Door Schedule; ALU/PVC hybrid, triple-glazed)
Window units installed — count | 42 | ASSUMED — A-003 lists 49 unique window callouts; sub-tags (a/b/c) represent multi-pane assemblies. 42 installed openings is mid-range; confirm with the architect
Window average supply price ($/unit, triple-glaze ALU/PVC) | 2800 | a long-standing window supplier pricing relationship (a 10-year supplier account, ref. supplier-relationship confirmation (May 2026)); Altus 2024/25 Canadian Cost Guide triple-glazed premium
Window installation labour ($/unit, incl. flashing/sealant) | 425 | BTY Group Market Intelligence Q4-2025 Ontario residential glazier labour; includes blueskin perimeter and spray foam per the architect note A-003
Exterior doors — entry (count) | 4 | A-003: D102/D103/D104 glass exterior + main entry — 4 exterior swing/glazed doors
Exterior door — supply+install rate ($/unit) | 4200 | Premium glazed exterior; Endura/Pella/the window supplier comparable; BTY Q4-2025
Garage door — 15 ft × 9 ft insulated (count) | 1 | A-003 schedule item D101: 'Garage door 15-0 x 9-0 Insulated R14'
Garage door — supply+install all-in ($) | 6800 | Wayne Dalton / Garaga insulated sectional; Ottawa residential premium; supply+install+opener rough-in
Interior doors — count (premium custom) | 22 | A-003 door tags D105–D112, D201–D205, D301–D313: ~22 interior swing/pocket/bifold doors (premium custom)
Interior door — supply+install rate ($/unit) | 750 | BTY Q4-2025 Ottawa residential premium; solid-core with concealed hinge
ELEVATOR & VERTICAL CIRCULATION
Elevator supply (cab + drive + controls), CONFIRMED ($) | 58000 | CONFIRMED — Owner owner correspondence (May 2026); 5 ft × 5 ft shaft per the architect A-201/A-202/A-203 stack
Elevator installation labour and TSSA commissioning ($) | 9500 | Ottawa TSSA-certified install; benchmark Otis/Savaria 2024/25 small residential
ROOFING
Sloped asphalt shingle roof — area, sq. ft. | 1450 | ASSUMED — A-204 roof plan; gable + hip area minus flat roof deck; verify with the architect
Flat roof / SBS membrane assembly — area, sq. ft. | 1100 | ASSUMED — A-204; includes rooftop patio substrate (3-ply SBS modified asphalt per architect general notes A-002 T2)
Composite decking on pedestals — rooftop, $/sf installed | 38 | BTY Q4-2025 + manufacturer (Trex/Bison pedestal) Ottawa installer composite at premium spec
STRUCTURAL
Roof trusses + floor joists supply, CONFIRMED ($) | 43000 | CONFIRMED — supplier quote per owner correspondence (May 2026) (supplier PDF attached to email)
RADIANT SLAB & MECHANICAL DRIVERS
Radiant in-floor — basement slab rate ($/sf installed) | 13 | Altus 2024/25 Canadian Cost Guide; PEX + manifold; serves basement habitable
Radiant in-floor — garage slab rate ($/sf installed) | 10 | Simpler single-zone garage loop; Ottawa contractor rate Q4-2025
GC FEE, CONTINGENCY, AND SCHEDULE
Schedule duration assumption (months, foundation to occupancy) | 15 | Client-facing schedule target 12-14 months foundation to occupancy. General conditions (Division N) are budgeted on a conservative 15-month-equivalent resourcing basis; the dollar allocation is held even where the calendar target is shorter.
Construction-management fee — % of approved hard costs | 16% | Construction-management fee 16% on a cost-plus / construction-management basis; monthly draw on % construction complete. Weighted toward firm scope the construction manager directly manages and procures.
Construction contingency — % of approved hard costs | 10% | AACE 18R-97 Class 3 estimate accuracy band lower bound; owner-held; drawn by written change order only
HST rate — Ontario (federal 5% + provincial 8%) | 13% | Excise Tax Act s.165; Ontario HST
BENCHMARKS — Ottawa CMA, 2026
Ottawa premium custom hard cost benchmark ($/sf habitable GBA) | 395 | Altus Group Canadian Cost Guide 2024/25 Ottawa CMA premium custom infill; BTY Q4-2025 Ontario residential infill (mid-band)
StatCan BCPI Ottawa CMA recent YoY (informational) | 4.5% | Statistics Canada Building Construction Price Index, Ottawa CMA, table 18-10-0135-01 (latest available)
General construction allowance (unallocated) — $ | 100000 | AACE 18R-97 Class 3 unallocated allowance; aligns the firm base hard cost with the client-approved budget pending trade tendering.

## Hard_Costs
CUSTOM SINGLE-DETACHED RESIDENCE (ELEVATOR-EQUIPPED) — HARD COSTS (detailed line items)
Grand total formula sums DETAIL ROWS ONLY (column G). Subtotals are display-only and reconciled on QA_Checks tab.
# | Div | Line item | Qty | Unit | Rate | Amount | Driver / formula | Source / basis | Confidence | Notes / exclusions
A. SITE WORK, DEMOLITION & TEMPORARY WORKS
1 | A | Demolition of existing bungalow — supply+haul+disposal | 1 | lump | 22000 |  | Lump-sum allowance; pre-1980 structure presumed; includes DSS prep | Ottawa demolition contractor Q4-2025; O.Reg 278/05 Designated Substances Survey (OHSA) basis prep | Benchmarked | Excludes hazmat abatement if DSS triggers
2 | A | Designated Substance Survey + report (asbestos/lead) | 0 | lump | 3500 | 0 | OHSA O.Reg 278/05 mandatory pre-demolition | Ottawa DSS provider benchmark Q4-2025 | Assumed | Reduces hazmat surprise risk; report deliverable required by demo contractor
3 | A | Site fencing, hoarding, signage (15-month duration) | 1 | lump | 2500 |  | Hoarding + safety signage; 15-month build | City of Ottawa hoarding by-law; Altus 2024/25 site overhead | Benchmarked | Includes refresh for high-traffic frontage
4 | A | Bin/disposal — mixed C&D waste (project total) | 1 | lump | 9500 |  | 8-10 bins over 15-month duration | Ottawa C&D disposal rates Q4-2025; landfill gate fees + haul | Benchmarked | Excludes hazmat-classified loads
5 | A | Site access, temporary driveway, mud mat | 0 | lump | 4500 | 0 | Crushed stone + geotextile temporary access | Ottawa infill standard; Altus 2024/25 | Benchmarked
6 | A | Temporary power — Hydro Ottawa temp service | 0 | lump | 3800 | 0 | Temp pole + temp meter; deposit refundable | Hydro Ottawa 2026 temporary service fees | Benchmarked | Refundable connection deposit excluded
7 | A | Temporary heat & winter protection (winter months) | 0 | lump | 9500 | 0 | Propane heat for concrete cure + framing enclosure | Altus 2024/25 winter premium Ottawa | Assumed | Scope depends on cure window timing
SUBTOTAL — Division A
B. EXCAVATION, GRADING & EARTHWORKS
8 | B | Bulk excavation — full basement + garage footprint | 1 | lump | 36000 |  | ~1780 sf footprint × full basement depth | Altus 2024/25 Ottawa excavation; clay conditions | Benchmarked | Soil disposal off-site; deeper excavation if elevator pit exceeds basement slab
9 | B | Elevator pit excavation + dewatering | 1 | lump | 6500 |  | Pit below basement slab per the architect elevator section | Ottawa elevator pit excavation Q4-2025 | Assumed | Coordinate depth with elevator supplier specification
10 | B | Shoring / underpinning allowance (infill adjacency) | 0 | allow | 0 | 0 | Allowance — confirm via geotech + the structural engineer review | AACE 18R-97 risk-driven allowance; Ottawa infill benchmark | Assumed | May not be required; carry until geotech complete
11 | B | Rough grading + lot drainage to City-approved plan | Inc | lump | 0 | 0 | Lot grading per City of Ottawa standards | Ottawa lot grading bond; City Lot Grading by-law | Benchmarked
SUBTOTAL — Division B
C. FOUNDATION, CONCRETE & WATERPROOFING
12 | C | Footings — strip + pad, poured concrete | 1 | lump | 26000 |  | Frost depth 1.2-1.5 m; poured incl. forming | Altus 2024/25 Ottawa residential concrete | Benchmarked
13 | C | Foundation walls — 10" concrete (per the architect A-002 W4) | 1 | lump | 48000 |  | 10" concrete walls; full basement perimeter | architect sheet A-002 detail; Altus 2024/25 | Benchmarked | Includes form, pour, strip, and rebar
14 | C | Basement slab — habitable area, 4" reinforced |  | sq.ft. | 11 |  | Assumptions!C7 × $11/sf | Altus 2024/25 residential slab | Benchmarked | Wire mesh + slab prep for radiant tubing rough-in
15 | C | Garage slab — 5" reinforced, sloped to drain |  | sq.ft. | 13 |  | Assumptions!C8 × $13/sf | Ottawa garage slab incl. floor drain | Benchmarked | Heavier slab section + sloped drainage
16 | C | Elevator pit walls + slab — concrete | 1 | lump | 8500 |  | Pit walls and slab below basement; small footprint | Ottawa concrete sub Q4-2025 | Assumed | Per TSSA pit dimensions of selected elevator
17 | C | Foundation waterproofing — Delta MS + weeping tile + sump | 1 | lump | 19500 |  | Full perimeter exterior waterproofing | OBC Div. B 9.13.4; Ottawa clay mandatory | Benchmarked | Includes sump pit, pump, and tile to sump
18 | C | Under-slab insulation — R10 XPS habitable basement |  | sq.ft. | 3.5 |  | Assumptions!C7 × $3.50/sf | OBC SB-12 Ottawa zone; XPS rigid | Benchmarked
SUBTOTAL — Division C
D. STRUCTURAL FRAMING (LUMBER, LVL, STEEL, TRUSSES)
19 | D | Roof trusses + floor joists — SUPPLY (CONFIRMED) | 1 | lump |  |  | Confirmed supplier quote | CONFIRMED — owner correspondence (May 2026) (supplier quote attached) | Confirmed | Truss/joist supply only; install in line below
20 | D | Truss & joist install labour (incl. crane mob) | 1 | lump | 16000 |  | Install labour + crane day rate | BTY Q4-2025 Ontario residential framing labour; Ottawa crane day rate | Benchmarked | Excludes engineered shop drawing review fees
21 | D | Lumber, sheathing, LVL beams (wall framing + miscellaneous) |  | sq.ft. | 11 |  | Assumptions!C12 × $1/sf wall framing material allowance | Random Lengths Composite Q2-2026 lumber index; Altus 2024/25 | Benchmarked | Material allowance for studs, plates, LVLs, sheathing
22 | D | Steel beams — garage 15-ft span + elevator shaft header | 1 | lump | 16000 |  | Per the structural engineer coordination (preliminary) | Ottawa structural steel fabricator Q4-2025; mill-only Bonnetterre/Cumberland rate | Assumed | Confirm sizing with the structural engineer before procurement
23 | D | Framing labour — walls + floor decks (above-grade habitable) |  | sq.ft. | 9 |  | Assumptions!C12 × $9/sf framing labour | BTY Q4-2025 Ontario residential framing labour | Benchmarked
SUBTOTAL — Division D
E. ROOFING — SLOPED, FLAT, ROOFTOP PATIO
24 | E | Sloped roof — asphalt shingles + R60 blown insulation |  | sq.ft. | 13 |  | Assumptions!C32 × $13/sf | OBC SB-12 Ottawa zone R60 mandatory; IKO Cambridge or equivalent | Benchmarked | Includes underlayment, ice-water, ridge vent
25 | E | Flat roof — 3-ply SBS modified asphalt + R50/R60 polyiso |  | sq.ft. | 22 |  | Assumptions!C33 × $22/sf | architect general note T2 (A-002); Siplast/IKO assembly | Benchmarked | Includes vapour barrier, tapered insulation, granular cap sheet
26 | E | Rooftop composite decking on pedestals |  | sq.ft. |  |  | Assumptions!C11 × Assumptions!C34 | Bison or Trex pedestal system; protects SBS membrane | Benchmarked
27 | E | Roof drains — primary + scupper overflow assemblies | 1 | lump | 6500 |  | OBC positive drainage; 2 primary + 1 scupper | OBC Div. B 9.26; Ottawa flat-roof standard | Benchmarked
28 | E | Rooftop guardrails — OBC-compliant 42" height | 1 | lump | 19500 |  | Aluminum or steel; OBC Div. B 9.8.8 | OBC mandatory for accessible rooftop; Ottawa fabricator | Benchmarked | Owner flagged as phaseable — confirm with the architect; without guardrails the rooftop cannot be occupied
29 | E | Flashings, eaves trough, soffit/fascia (sloped + flat) | 1 | lump | 8500 |  | Aluminum eavestrough + fascia + soffit | Ottawa standard residential roofing trim | Benchmarked
SUBTOTAL — Division E
F. EXTERIOR ENVELOPE & CLADDING
30 | F | W1 stone supply — natural white stone (front facade) |  | sq.ft. | 9 |  | Assumptions!C15 × $9/sf (supply only — material per client) | CONFIRMED supply rate — owner correspondence (May 2026) | Confirmed | Material per client; install labour separate
31 | F | W1 stone install labour + mortar + accessories |  | sq.ft. | 22 |  | Assumptions!C15 × $22/sf install labour | Ottawa mason labour Q4-2025; BTY Q4-2025; scaffolding included | Benchmarked | Premium hand-laid; includes scaffolding mobilization
32 | F | W2 aluminum wood-look paneling — supply+install |  | sq.ft. | 58 |  | Assumptions!C16 × $58/sf supply+install | Architectural ACM/aluminum panel; BTY Q4-2025 Ottawa | Benchmarked | Includes sub-framing, omega bars, fasteners
33 | F | W3 stucco (Adex-RS or equivalent) supply+install |  | sq.ft. | 21 |  | Assumptions!C17 × $21/sf | Adex-RS premium synthetic stucco; Ottawa applicator Q4-2025 | Benchmarked | Includes base coat, mesh, finish coat
34 | F | Air/vapour barrier (Tyvek CommercialWrap) full envelope |  | sq.ft. | 1.5 |  | Assumptions!C12 × $1.50/sf prorated | DuPont Tyvek; OBC SB-12 air barrier requirements | Benchmarked | All penetrations taped
35 | F | Continuous exterior insulation — R5 rigid (where architect W1/W3) |  | sq.ft. | 4.5 |  | Assumptions!C12 × $4.50/sf prorated | OBC SB-12 Ottawa zone; XPS continuous | Benchmarked
36 | F | Cavity insulation — R22/R28 batt + R28 SPF at W2 | 1 | lump | 18500 |  | architect W1/W3 cavity batt + W2 closed-cell SPF | the architect wall details A-002; Altus 2024/25 | Benchmarked
37 | F | Wood accents — exterior trim, soffits, beam wraps | 1 | lump | 8500 |  | Cedar or thermally-modified accent; architect concept | architect cover description; Ottawa millwork Q4-2025 | Benchmarked
SUBTOTAL — Division F
G. WINDOWS & EXTERIOR DOORS (triple-glazed ALU/PVC per the architect A-003)
38 | G | Triple-glazed ALU/PVC windows — supply |  | ea |  |  | Assumptions!C19 × Assumptions!C20 | a long-standing window supplier direct (supplier account); Altus 2024/25 premium triple-glazed | Benchmarked | Confirm final count with the architect; lead time 12-16 weeks
39 | G | Window installation labour + flashing + spray foam |  | ea |  |  | Assumptions!C19 × Assumptions!C21 | BTY Q4-2025 glazier labour; architect A-003 install notes | Benchmarked | Blueskin perimeter, foam, sill pan, exterior caulking
40 | G | Exterior entry doors — supply+install |  | ea |  |  | Assumptions!C22 × Assumptions!C23 | Endura / the window supplier exterior; BTY Q4-2025 | Benchmarked | 4 exterior swinging/glazed leaves per A-003
41 | G | Insulated garage door (15' × 9' sectional) |  | ea |  |  | Assumptions!C24 × Assumptions!C25 | Wayne Dalton / Garaga insulated; opener rough-in incl. | Benchmarked | R14 per A-003 schedule
SUBTOTAL — Division G
H. MECHANICAL — HVAC, RADIANT, GAS, CONTROLS
42 | H | Radiant in-floor — basement habitable |  | sq.ft. |  |  | Assumptions!C7 × Assumptions!C38 | Altus 2024/25 radiant glycol system | Benchmarked | PEX + manifold; integrated with boiler
43 | H | Radiant in-floor — garage |  | sq.ft. |  |  | Assumptions!C8 × Assumptions!C39 | Single-zone garage loop | Benchmarked
44 | H | Cold-climate air-source heat pump + air handler + ducting | 1 | lump | 36000 |  | Mitsubishi Hyper Heat or equivalent; 2-storey + basement | Altus 2024/25 cold-climate ASHP; Ottawa min heating standard | Benchmarked
45 | H | HRV — heat-recovery ventilation (Lifebreath or equivalent) | 1 | lump | 9500 |  | OBC Div. B 9.32 mandatory | OBC mandatory; Ottawa residential | Benchmarked | Sized for 4-bedroom envelope
46 | H | Boiler + glycol mechanical plant for radiant | 1 | lump | 18000 |  | Condensing boiler + glycol loop manifold + pumps | Altus 2024/25 boiler plant | Benchmarked | Tied to tankless DHW for combined plant if compatible
47 | H | Gas service piping + interior distribution (Enbridge tie) | 1 | lump | 7500 |  | Service lateral + interior gas piping for boiler/range/fireplace | Enbridge 2026 residential connection; Ottawa piping labour | Benchmarked
48 | H | Controls + zoning + commissioning | 1 | lump | 5500 |  | Multi-zone thermostat / smart controls; commissioning | Altus 2024/25; smart controls premium | Benchmarked
SUBTOTAL — Division H
I. PLUMBING — ROUGH-IN, FIXTURES, SERVICE
49 | I | DWV + supply rough-in (5 BA + kitchen + laundry + basement) | 1 | lump | 38000 |  | 5 BA + kitchen + laundry + basement utility | BTY Q4-2025 plumbing labour Ottawa residential premium | Benchmarked
50 | I | Plumbing fixtures + fittings — premium custom | 0 | lump | 0 | 0 | Grohe/Kohler-level allowance | Altus 2024/25 high-end residential fixture allowance | Selection | OWNER-DIRECTED SELECTION — carried in Selections budget (low $25,000 / high $45,000); excluded from firm base hard cost. Confirm finish spec with client
51 | I | Tankless DHW — Navien NPE-240A or equivalent | 1 | lump | 4800 |  | Condensing tankless integrated where possible with boiler | Navien/Rinnai standard premium spec | Benchmarked
52 | I | Water service from City + sewer lateral connection | 1 | lump | 8500 |  | Service lateral activation incl. fees | City of Ottawa 2026 service connection schedule | Benchmarked
53 | I | Hose bibs, sump connections, miscellaneous | 1 | lump | 2800 |  | Frost-free hose bibs + sump | Standard residential | Benchmarked
SUBTOTAL — Division I
J. ELECTRICAL & LOW-VOLTAGE
54 | J | 200A service + panel + sub-panel + full circuit rough-in | 1 | lump | 32000 |  | Service entrance + main + sub | BTY Q4-2025 Ontario electrical labour | Benchmarked
55 | J | Lighting fixtures + switches + dimmers (premium allowance) | 0 | lump | 0 | 0 | Recessed + decorative; LED throughout | Altus 2024/25 premium fixture allowance | Selection | OWNER-DIRECTED SELECTION — carried in Selections budget (low $16,000 / high $32,000); excluded from firm base hard cost. Confirm spec with client; decorative excluded above allowance
56 | J | Smoke/CO detection — interconnected (OBC compliant) | 1 | lump | 2200 |  | OBC Div. B 9.10.19 (smoke) + 9.32.3 (CO) | OBC mandatory | Benchmarked
57 | J | EV charger rough-in — Level 2 (40A/240V garage) | 1 | lump | 2500 |  | Dedicated 40A circuit + EVSE rough-in | Ottawa 2026 standard EV rough-in | Benchmarked | EVSE unit by client
58 | J | Central vacuum (supply + install) — confirmed in architect set | 1 | lump | 4200 |  | Beam or NuTone; architect plans show CV | architect plans; standard Ottawa premium custom | Benchmarked
59 | J | Low-voltage rough-in (CAT6, coax, speakers, security) | 1 | lump | 6500 |  | Premium custom rough-in spec | Altus 2024/25 low-voltage rough-in | Assumed | Equipment/programming by separate contract
60 | J | Exterior lighting (facade + landscape + soffit) | 1 | lump | 4500 |  | LED downlights + path lighting | Ottawa exterior lighting Q4-2025 | Benchmarked
SUBTOTAL — Division J
K. ELEVATOR
61 | K | Elevator supply — cab, drive, controls (CONFIRMED) | 1 | lump |  |  | Owner-confirmed quote | CONFIRMED — owner correspondence (May 2026) | Confirmed | 5×5 shaft per the architect A-201/202/203
62 | K | Elevator installation + TSSA certification + commissioning | 1 | lump |  |  | TSSA-certified install | Ontario TSSA certification mandatory | Benchmarked | Includes commissioning + occupancy permit
SUBTOTAL — Division K
L. INTERIOR FINISHES — DRYWALL, FLOORING, MILLWORK, TILE, PAINT
63 | L | Drywall, taping, sanding — all habitable (incl. Type X in garage/elevator) | 1 | lump | 36000 |  | 5/8 Type X in garage/elevator shaft per OBC | OBC fire resistance; BTY Q4-2025 drywall labour | Benchmarked
64 | L | Interior partition insulation (acoustic + thermal) | 1 | lump | 12500 |  | Mineral wool batts at acoustic-rated partitions | architect M1-M5 partition types per A-002 | Benchmarked
65 | L | Interior doors — supply+install |  | ea |  |  | Assumptions!C26 × Assumptions!C27 | Premium solid-core; BTY Q4-2025 | Benchmarked
66 | L | Trim — base, casing, crown, jambs (premium profile) | 1 | lump | 26000 |  | Painted MDF or wood; premium profile | Ottawa joinery Q4-2025; Altus 2024/25 premium | Benchmarked
67 | L | Kitchen cabinetry + countertops (premium custom) | 0 | lump | 0 | 0 | Custom flat-panel + stone counter + waterfall island | Ottawa custom kitchen Q4-2025; Altus 2024/25 premium | Selection | OWNER-DIRECTED SELECTION — carried in Selections budget (low $65,000 / high $110,000); excluded from firm base hard cost. Confirm spec with client; appliance allowance separate
68 | L | Bathroom millwork, tile, glass, vanities — 5 bathrooms | 0 | lump | 0 | 0 | Premium custom 5 BA package | Ottawa premium custom bathrooms Q4-2025 | Selection | OWNER-DIRECTED SELECTION — carried in Selections budget (low $55,000 / high $95,000); excluded from firm base hard cost. Confirm fixture & finish spec with client
69 | L | Hardwood flooring — engineered, above grade + basement habitable | 0 | sq.ft. | 0 | 0 | Assumptions!C12 × $11/sf supply+install | Altus 2024/25 engineered hardwood premium | Selection | OWNER-DIRECTED SELECTION — carried in Selections budget (low $50,985 / high $80,000); excluded from firm base hard cost. Tile in wet rooms allowance separate
70 | L | Stair + railing assembly (incl. open-to-below) | 1 | lump | 22000 |  | Open riser feature + glass guardrail at open-to-below | architect A-551 stair sheet + open-to-below feature | Benchmarked
71 | L | Painting — primer + 2 coats full house | 1 | lump | 22500 |  | Premium washable finish full house | Ottawa painting Q4-2025; BTY Q4-2025 | Benchmarked
72 | L | Closet systems + built-ins allowance | 0 | lump | 0 | 0 | Custom closet systems + library/feature built-ins | Ottawa custom millwork allowance | Selection | OWNER-DIRECTED SELECTION — carried in Selections budget (low $18,000 / high $35,000); excluded from firm base hard cost. Confirm scope with client
73 | L | Appliance allowance (cooking, refrigeration, dishwasher) | 0 | allow | 0 | 0 | Premium tier allowance | Ottawa premium appliance allowance Q4-2025 | Selection | OWNER-DIRECTED SELECTION — carried in Selections budget (low $22,000 / high $55,000); excluded from firm base hard cost. Final spec by client
SUBTOTAL — Division L
M. SITE COMPLETION, LANDSCAPING & RESTORATION
74 | M | Driveway — asphalt or stamped concrete | 1 | lump | 15500 |  | Includes curb cut if required | Ottawa driveway Q4-2025 | Benchmarked
75 | M | Walkways, front entrance hardscape | 1 | lump | 9500 |  | Stone or pavers entrance walk | Ottawa hardscape Q4-2025 | Benchmarked
76 | M | Landscaping, sod, planting, rooftop greenscape | 1 | lump | 14000 |  | Grade + rooftop planters allowance | Allowance — Ottawa landscape contractor | Assumed | Confirm rooftop greenscape scope with architect/client
77 | M | Fencing — lot perimeter (privacy) | 1 | lump | 9500 |  | Wood or steel privacy fence | Ottawa fencing Q4-2025 | Benchmarked
78 | M | Final grading + drainage tie to lot grading plan | 1 | lump | 4500 |  | Final compliance grading | Ottawa lot grading bond | Benchmarked
SUBTOTAL — Division M
N. GENERAL CONDITIONS & DIRECT SITE OVERHEAD (15-month build)
79 | N | Site superintendent — CM-supplied (allocated) |  | month | 4200 |  | Assumptions!C41 months × $4,200 allocated | the CM project manager cost; allocated portion of senior supervisor | Benchmarked | Allocation reflects shared resourcing
80 | N | Project coordination + procurement (the CM project manager time) |  | month | 2500 |  | Assumptions!C41 months × $1,500 | the CM project manager allocated; preconstruction + procurement | Benchmarked
81 | N | Builder's risk + general liability insurance | 1 | lump | 14500 |  | All-risk + $2M liability minimum | Intact/Aviva builder's risk Q4-2025; ~0.85% of construction value | Benchmarked
82 | N | Site safety, OBC compliance, WHMIS, signage | 1 | lump | 4500 |  | OBC site safety + signage compliance | OBC + OHSA site safety | Benchmarked
83 | N | Cleaning + final clean / occupancy turnover | 1 | lump | 5500 |  | Progressive + final pre-occupancy clean | Ottawa premium custom turnover | Benchmarked
84 | N | Protection of finishes during construction | 1 | lump | 4500 |  | Floor/wall protection through occupancy phases | Standard custom residential | Benchmarked
SUBTOTAL — Division N
| O. GENERAL CONSTRUCTION ALLOWANCE (UNALLOCATED — AACE CLASS 3) | General construction allowance — unallocated | 1 | lump | 100000 |  | AACE 18R-97 Class 3 provision for scope not yet itemised at this estimate stage | AACE International RP 18R-97; carried to align firm base with the client-approved budget pending trade tendering | Assumed | Drawn against itemised trades as scope firms up at tender; reconciled at substantial completion
TOTAL HARD COSTS (sum of detail rows only — see QA_Checks)

## Soft_Costs
CUSTOM SINGLE-DETACHED RESIDENCE (ELEVATOR-EQUIPPED) — SOFT COSTS (detailed line items)
Grand total formula sums DETAIL ROWS ONLY (column G). Subtotals are display-only and reconciled on QA_Checks tab.
# | Div | Line item | Qty | Unit | Rate | Amount | Driver / formula | Source / basis | Confidence | Notes / exclusions
P. DESIGN, ENGINEERING & PROFESSIONAL FEES
1 | P | Architecture — the project architect (CA + site review + closeout) | 1 | lump | 68000 |  | Construction admin + site review for stamped permit set | the architect the architect's project file; engagement basis as project architect | Benchmarked | Permit drawings already complete; CA scope through closeout
2 | P | Structural engineering — the structural engineer (foundation, framing, elevator) | 1 | lump | 26000 |  | SE design, review, site visits | Confirmed engineer per structural-engineer confirmation (May 2026) | Benchmarked | Foundation + framing + elevator + steel coordination
3 | P | MEP engineering (mechanical/electrical/plumbing drawings) | 1 | lump | 14500 |  | Required for permit; radiant + HRV + elevator | Ottawa MEP Q4-2025; required for permit submission | Benchmarked
4 | P | Land survey — building location + as-built | 2 | ea | 3500 |  | AOLS-certified pre- and post-construction surveys | Ottawa AOLS survey firm Q4-2025 | Benchmarked
5 | P | Geotechnical investigation — soil + elevator pit | 1 | lump | 6500 |  | Bearing capacity + frost depth + elevator pit | Ottawa geotech Q4-2025; clay conditions | Benchmarked | Required pre-foundation by SE
6 | P | BCIN permit agent (if not handled by the architect) | 1 | allow | 3000 |  | Allowance only — may be $0 if the architect handles directly | Ottawa BCIN agent Q4-2025 | Assumed
7 | P | Legal — GC contract, holdback, lien admin | 1 | lump | 9500 |  | CCDC 2 2020 drafting + holdback admin | Construction Act (Ontario) R.S.O. 1990 c.C.30 (as amended); CCDC standard form | Benchmarked | First-client engagement justifies legal review
SUBTOTAL — Division P
Q. CITY OF OTTAWA — PERMITS & UTILITY FEES
8 | Q | City of Ottawa building permit fee (residential) | 1 | lump | 18500 |  | Estimated on declared construction value | City of Ottawa By-law 2014-149 (Building Code Act admin); 2026 fee schedule | Benchmarked | Final fee assessed at issuance on declared value
9 | Q | Plumbing & drainage permit (separate) | 1 | lump | 1500 |  | Separate plumbing permit | City of Ottawa plumbing permit schedule 2026 | Benchmarked
10 | Q | Mechanical (HVAC) permit | 1 | lump | 950 |  | Mechanical permit for HRV/radiant | City of Ottawa mechanical schedule 2026 | Benchmarked
11 | Q | Demolition permit | 1 | lump | 750 |  | Single demolition permit for existing bungalow | City of Ottawa demolition permit 2026 | Benchmarked
12 | Q | Road occupancy / encroachment permit | 1 | lump | 4000 |  | For crane, concrete pump, delivery access | City of Ottawa road occupancy 2026 | Benchmarked
13 | Q | Hydro Ottawa — 200A service connection (new) | 1 | lump | 3200 |  | New residential service entrance | Hydro Ottawa 2026 connection schedule | Benchmarked | Refundable deposit excluded
14 | Q | Enbridge gas — service activation | 1 | lump | 1200 |  | Service lateral activation | Enbridge Gas 2026 residential connection schedule | Benchmarked
SUBTOTAL — Division Q
R. DEVELOPMENT CHARGES & PLANNING LEVIES
15 | R | City of Ottawa development charge — 1 single-detached dwelling | 1 | ea | 41500 |  | Annual Apr 1 indexing; 2026 SDD rate (approx — verify at issuance) | City of Ottawa DC By-law (current as amended); annual indexing per April schedule. Bill 23 exemptions verified inapplicable to single-detached principal residence | Assumed | Confirm with City of Ottawa at permit; demolition credit may reduce
16 | R | Cash-in-lieu of parkland (Ottawa s.42 Planning Act) | 1 | ea | 9500 |  | Residential parkland levy estimate | City of Ottawa Parkland Dedication By-law 2022-280; Planning Act s.42 | Assumed | Final assessment at building permit
17 | R | OCDSB education development charge | 1 | ea | 1750 |  | Ottawa-Carleton DSB EDC 2026 | OCDSB EDC By-law (2024); Education Act s.257.54 | Assumed | Confirm applicable board at permit
18 | R | Demolition credit (existing dwelling unit on site) | 1 | ea | -4500 |  | Demolition credit applied to DC | Ottawa DC By-law: existing dwelling demolition credit policy | Assumed | Credit applied at permit issuance; verify amount
SUBTOTAL — Division R
S. INSURANCE, FINANCING & MISC SOFT
19 | S | Owner's property/title insurance during construction | 1 | lump | 2800 |  | Owner-held; ~0.15% of construction value | Intact / Aviva 2026 owner construction policy | Assumed | Owner-procured; budget placeholder
20 | S | Tarion — NOT applicable (owner-occupied custom, no vendor enrolment) | 1 | ea | 0 |  | Owner-occupied owner-build; Tarion enrolment not triggered | ONHWP Act; Tarion vendor enrolment rules — confirms not required for owner-occupied custom build | Confirmed | If client later sells within 12 months, self-supply HST + Tarion implications must be reviewed
21 | S | Project owner reserve — utility deposits, miscellaneous | 1 | lump | 4500 |  | Refundable deposits + miscellaneous owner soft costs | Standard Ottawa custom build | Assumed
SUBTOTAL — Division S
TOTAL SOFT COSTS (sum of detail rows only — see QA_Checks)

## Selections
CUSTOM SINGLE-DETACHED RESIDENCE (ELEVATOR-EQUIPPED) — OWNER-DIRECTED SELECTIONS BUDGET
Owner-spec items. Low = the premium-custom allowance carried in the base case. High = a defensible ceiling reflecting the most expensive specification within the design intent. Selections above the ceiling are administered as written change orders.
# | Selection | Low — allowance ($) | High — ceiling ($) | Spec range / notes
1 | Kitchen cabinetry & countertops | 65000 | 110000 | Custom flat-panel + stone counter base; high = full natural-stone slab, integrated panel-ready appliance fronts.
2 | Bathroom millwork, tile, vanities (5 bathrooms) | 55000 | 95000 | Premium custom 5-bath base; high = honed natural-stone slabs, custom glass enclosures, designer vanities.
3 | Plumbing fixtures & fittings | 25000 | 45000 | Mid-premium base; high = top-tier fittings, freestanding tubs, multi-jet showers.
4 | Engineered hardwood flooring | 50985 | 80000 | Premium engineered base ($11/sf); high = wide-plank European white oak, herringbone or chevron lay.
5 | Interior lighting fixtures | 16000 | 32000 | LED recessed + decorative base; high = designer pendants, statement chandeliers, integrated linear.
6 | Closet systems & built-ins | 18000 | 35000 | Custom closets + feature built-ins base; high = full walk-in millwork packages, integrated lighting.
7 | Appliance package (cooking, refrigeration, dishwasher) | 22000 | 55000 | Premium-tier base; high = full luxury suite, integrated columns, built-in coffee.
| TOTAL — SELECTIONS RANGE |  |  | Low carried in base case; high brackets the owner-driven ceiling.
Low-end selections add ($/sf habitable)
High-end selections add ($/sf habitable)

## GC_Fee_Proposal
OWNER-DIRECTED RESIDENCE — CONSTRUCTION-MANAGEMENT FEE SUMMARY (in-workbook)
This tab summarises the fee structure. The full client-facing proposal is delivered as a separate document.
FEE BASIS
Construction-management fee |  | 16% of final approved base hard costs (construction-management basis). All trade costs flow at cost; no trade markup unless explicitly approved in writing. Owner pays trades directly through a managed accounts-payable platform integrated with QuickBooks Online; the only payable to the construction manager is the monthly fee.
Fee rate (% of hard costs) |  | Editable on Assumptions; default 15%
Contingency basis |  | 10% of final approved hard costs. Owner-held. Drawn only on signed change orders.
Schedule basis (months) |  | Foundation to substantial completion. 15 months is the working assumption; revise after permit-issuance schedule baseline.
WHAT THE FEE INCLUDES
Pre-construction | — | Document review, value engineering, procurement strategy, schedule baseline, subcontractor pre-qualification, permit liaison.
Procurement & tendering | — | Trade RFP packages, scope clarification, bid leveling, recommendation memos to owner, contract execution for trades.
Construction administration | — | RFI management, submittals review, schedule maintenance, cost report, change order administration, owner reporting cycle.
Site coordination & supervision | — | Daily site presence (allocated supervisor), trade scheduling, quality control inspection, OBC site safety compliance, environmental controls.
Cost reporting & change management | — | Monthly written cost report against the approved budget; written change orders for any scope variance; cost-to-complete forecast.
Inspections, occupancy, closeout | — | City of Ottawa inspection coordination, TSSA elevator certification, occupancy permit, deficiency list, warranty turnover.
WHAT THE FEE EXCLUDES
Trade costs | — | Pass through at cost; no markup. Sales tax on trade invoices is owner cost.
Consultant fees | — | Architecture, structural, MEP, geotech, survey, legal — all paid directly by owner or pass-through.
Permits & municipal | — | Building, plumbing, mechanical, demolition, road occupancy, hydro, gas, DCs, parkland CIL — all owner-cost.
HST | — | 13% on the construction manager fee and on taxable construction services. Owner-occupied custom home — no ITC recovery. Embedded as cost.
Owner-directed changes | — | Any scope addition or finish upgrade after contract execution. Treated as Change Order.
Financing & legal | — | Owner financing, legal fees for owner. the CM's legal for the GC contract itself is in Soft Costs.
Environmental/hazmat surprise | — | Unknown hazardous material remediation discovered during demolition or excavation — owner-cost contingency item.
PAYMENT STRUCTURE
Billing cadence | — | Monthly draw on percentage of construction complete, as reported in the monthly cost report.
Reconciliation | — | At substantial completion, fee is reconciled to 15% of final approved hard costs. Over- or under-draws are settled in the closeout invoice.
Holdback compliance | — | 10% statutory holdback on each progress payment under the Construction Act (Ontario) R.S.O. 1990 c.C.30 (as amended); released after lien period expiry.

## Risk_Register
CUSTOM SINGLE-DETACHED RESIDENCE (ELEVATOR-EQUIPPED) — RISK REGISTER (probability-impact-exposure)
Per PMI Construction Extension PMBOK 7th ed. 2022. Expected exposure = probability × impact (midpoint). Owner = decision authority.
# | ID | Risk description | Probability | Impact ($, mid) | Exposure ($) | Owner | Mitigation
1 | R-01 | Permit delay — City of Ottawa building permit cycle 3-5 months; radiant + elevator + rooftop add review complexity | 40% | 32500 |  | the CM project manager | Submit permit immediately; pre-consult with City building dept; ensure TSSA elevator spec sheet accompanies permit pkg; the architect handles RFIs
2 | R-02 | Geotechnical surprise — elevator pit dewatering or unsuitable soils requiring deeper footings or pile transition | 30% | 32000 |  | Owner / the structural engineer | Commission geotechnical investigation before permit submission; the structural engineer reviews adjacency conditions; carry shoring allowance
3 | R-03 | Shoring / underpinning of adjacent property required (infill adjacency) | 20% | 28000 |  | Owner / the structural engineer | Pre-construction adjacent-property condition survey; party-wall extension on builder's risk insurance; budget allowance in Hard Costs
4 | R-04 | Window lead time — 12-16 weeks; delays envelope closing and downstream trades | 45% | 24000 |  | the CM project manager / Owner | Place window order at permit application stage (do not wait for issuance); the window supplier lead-time confirmation required before order
5 | R-05 | Elevator lead time / spec change after deposit | 20% | 18000 |  | Owner | Lock elevator spec in GC contract before permit; treat as provisional sum if spec not finalized; TSSA-pre-approved supplier shortlist
6 | R-06 | Exterior cladding takeoff variance — W1/W2/W3 areas are takeoff assumptions; actual architect quantity-surveyor takeoff may vary materially | 55% | 24000 |  | the CM project manager / the architect | Commission architect quantity-surveyor exterior takeoff before client presentation; do not commit cladding areas without takeoff backup
7 | R-07 | Rooftop guardrail OBC compliance — owner suggested phasing; OBC Div. B 9.8.8 requires for occupancy | 30% | 8000 |  | Owner / the architect | Confirm with the architect whether guardrails required for occupancy permit before agreeing to defer; budget includes guardrails
8 | R-08 | Winter construction premium — Ottawa winters add concrete cure heating, framing enclosures, schedule risk | 50% | 13000 |  | the CM project manager | Sequence foundation pour for spring/summer where possible; budget temp heat $9,500 in Site Overhead
9 | R-09 | Client scope creep — premium custom owner may upgrade finishes, kitchen, rooftop scope mid-construction | 65% | 55000 |  | Owner / the CM project manager | Formal Change Order process embedded in GC contract; CO required before work proceeds; monthly cost report flags trajectory
10 | R-10 | Subcontractor availability — Ottawa custom trades booked 3-6 months ahead in 2025-26 | 40% | 12000 |  | the CM project manager | Lock priority trades (mason, window, elevator, mechanical) at permit application; tier-2 backups identified for each trade category
11 | R-11 | First external-client GC engagement risk — operational-services first; new authorities, new comms patterns | 25% | 35000 |  | Firm leadership | CCDC 2 2020 standard contract; legal review of contract; weekly owner cadence; written records of all material decisions
12 | R-12 | HST treatment uncertainty — owner tax advisor confirms NRRP eligibility / Ontario New Housing Rebate ($24K) at substantial completion | 25% | 12000 |  | Owner tax advisor | Owner to engage tax advisor before substantial completion; budget assumes embedded HST without rebate recovery
13 | R-13 | DC indexing — Ottawa DCs index annually April 1; project spans two DC years | 30% | 5500 |  | the CM project manager | Pay DCs at permit issuance; confirm DC rate lock-in policy with City of Ottawa
14 | R-14 | Municipal fee/utility connection schedule changes — Hydro Ottawa, Enbridge mid-project rate changes | 20% | 4000 |  | the CM project manager | Apply for connections immediately after permit issuance; lock current rate schedule
TOTAL EXPECTED RISK EXPOSURE
|  | Coverage check — contingency vs expected risk |  |  |  |  | Positive = contingency covers expected risk; negative = topup needed

## Sources_Method
CUSTOM SINGLE-DETACHED RESIDENCE (ELEVATOR-EQUIPPED) — SOURCES & METHOD
Authoritative basis for every major assumption. Cite this tab in client meetings.
Domain | Citation
Architectural basis | Project architect (identity withheld), stamped For Permit (Rev 1) — 31-sheet A1 permit set. Architect address, contact email, and BCIN withheld for anonymisation.
First-pass budget (audited & rebuilt) | internal: the first-pass internal budget (May 2026) (May 2026). Audit findings: (1) Hard_Costs!F94 and Soft_Costs!F28 each summed subtotal AND detail rows — totals were approximately doubled; (2) Summary tab contained broken refs (C10=B11/B15 where B11 was blank; B15=B7+B11+B13+B14 referenced blank cells); (3) above-grade GFA understated at 2,600 sf vs plans 3,315 sf; (4) window count understated at 35 vs schedule 49 unique tags; (5) declared AACE Class 5 rather than client-target Class 3. All defects corrected in this rebuild.
Structural reference (methodology only) | a separate internal CMHC MLI Select rental reference model — used as reference for risk register format and Sources_Method structure ONLY. No cost values transferred (per client instruction). the reference rental model is a CMHC MLI Select rental project — its HST self-supply / NRRP / PBRH analysis is INAPPLICABLE to the project (owner-occupied custom).
Owner-confirmed values | owner correspondence (May 2026) (Re: the project): elevator supply $58,000; roof trusses + floor joists supply $43,000 (supplier quote attached to email); exterior stone supply $9/sf MATERIAL only (install labour separate). Window supplier preference: the window supplier (a 10-year relationship per the same correspondence).
Cost benchmarks — premium custom | Altus Group, Canadian Cost Guide 2024/25 — Ottawa CMA premium custom infill residential ($/sf habitable GBA basis).
Cost benchmarks — Ontario residential | BTY Group, Market Intelligence Q4-2025 — Ontario residential infill cost/labour bands.
Cost escalation index | Statistics Canada, Building Construction Price Index, Ottawa CMA — table 18-10-0135-01.
Lumber index | Random Lengths Composite Index Q2-2026.
Building code basis | Ontario Building Code O.Reg 332/12 (as amended), Supplementary Standard SB-12 (energy efficiency Ottawa zone). Specific provisions cited: Div. B 9.8.8 (rooftop guardrails ≥42"), 9.10.19 (smoke alarms), 9.13.4 (foundation waterproofing), 9.26 (roof drainage), 9.32 (HRV mandatory).
Hazmat / demolition | O.Reg 278/05 — Designated Substances in Demolition (OHSA). Mandates pre-demolition Designated Substance Survey when targeting pre-1980 buildings.
Tree protection | City of Ottawa By-law 2020-340 — Tree Protection. Confirm protected trees at the project before site mobilization.
Building permit rates | City of Ottawa By-law 2014-149 (Building Code Act administration); 2026 fee schedule. Permit fee assessed on declared construction value.
Development charges | City of Ottawa Development Charges By-law (current; April 1 annual indexing). the project is single-detached principal residence — Bill 23 More Homes Built Faster Act 2022 exemptions for ADUs do not apply to this principal dwelling.
Parkland CIL | City of Ottawa Parkland Dedication By-law 2022-280; Planning Act R.S.O. 1990 c.P.13 s.42 as amended by Bill 23.
Education DC | Education Act R.S.O. 1990 c.E.2 s.257.54; Ottawa-Carleton DSB EDC By-law 2024.
HST treatment | Excise Tax Act R.S.C. 1985 c.E-15 — Owner-occupied custom build: no self-supply event under s.191(3) (no sale or rental). NRRP per ETA s.256.2 inapplicable (no rental). PBRH per ETA s.256.2.1 inapplicable (no multi-unit rental). Ontario New Housing Rebate available via Ontario Taxation Act 2007 c.11 Sch.A (max $24,000) — owner tax advisor must confirm eligibility based on purchase/construction price thresholds.
Holdback / lien | Construction Act (Ontario) R.S.O. 1990 c.C.30 (as amended). 10% statutory holdback on each progress payment; lien expiry monitoring required for fee finalization.
TSSA elevator certification | Technical Standards & Safety Authority, Elevating Devices Regulation O.Reg 209/01. Mandatory certification before occupancy of building containing elevator.
Estimating methodology | AACE International Recommended Practice 18R-97 — Cost Estimate Classification System. This estimate is presented as Class 3 (-10/-20 to +10/+30) on the basis of stamped architectural set; many trade-line confidence flags are Benchmarked rather than Quoted, which is reflected in the Confidence column on Hard_Costs/Soft_Costs.
Risk methodology | Project Management Institute, Construction Extension to the PMBOK Guide, 7th edition, 2022. Probability × impact midpoint = expected exposure.
Standard contract form | CCDC 2 — Stipulated Price Contract (2020), modified for cost-plus-fee engagement. Standard Canadian Construction Documents Committee form, owner-friendly amendments to be drafted by the firm's counsel.
Premium window basis | a long-standing window supplier — direct supplier relationship, a supplier account of 10+ years (supplier-relationship confirmation (May 2026)). Triple-glazed ALU/PVC hybrid per architect sheet A-003 specifications (NAFS AAMA/WDMA/CSA 101/I.S.2/A440-08).
Premium stone basis | an Ottawa stone supplier (per supplier correspondence). Confirmed material rate $9/sf (the Owner). Install labour Ottawa mason benchmark.
Premium tile basis | an Ottawa tile supplier — supplier account (firm correspondence).

## QA_Checks
CUSTOM SINGLE-DETACHED RESIDENCE (ELEVATOR-EQUIPPED) — QA / AUDIT CHECKS
Independent reconciliation of all totals. PASS/FAIL formulas prove no double-counting and no broken references.
# | Audit check | Computed value | Expected | PASS/FAIL & notes
1 | Hard cost grand total formula (Hard_Costs!G119) — sum of detail rows
2 | Hard cost — sum of SUBTOTAL ROWS (independent cross-check)
3 | Soft cost grand total formula (Soft_Costs!G36) — sum of detail rows
4 | Soft cost — sum of SUBTOTAL ROWS (independent cross-check)
5 | Construction-management fee — 16% of base hard costs
6 | Contingency — 10% of base hard costs
7 | TPC pre-HST (base case) = Base hard + Soft + Selections(low) + Fee + Contingency
8 | Total construction per sf (base hard + selections low) — sanity vs Ottawa premium-custom benchmark
9 | Soft cost as % of total construction (base hard + selections low) — typical 9-14% premium custom Ottawa |  | 11.5%
| Memo — base hard cost alone per sf (selections excluded) |  |  | Informational: firm base excludes owner-directed selections, so it sits below the all-in premium-custom benchmark by design.
CONFIDENCE FLAG SUMMARY (counts and $ exposure by flag)
| Hard_Costs lines flagged 'Confirmed' |  |  | Count and $ exposure
| Hard_Costs lines flagged 'Quoted' |  |  | Count and $ exposure
| Hard_Costs lines flagged 'Benchmarked' |  |  | Count and $ exposure
| Hard_Costs lines flagged 'Assumed' |  |  | Count and $ exposure
| Hard_Costs lines flagged 'TBD' |  |  | Count and $ exposure
| Soft_Costs lines flagged 'Confirmed' |  |  | Count and $ exposure
| Soft_Costs lines flagged 'Quoted' |  |  | Count and $ exposure
| Soft_Costs lines flagged 'Benchmarked' |  |  | Count and $ exposure
| Soft_Costs lines flagged 'Assumed' |  |  | Count and $ exposure
| Soft_Costs lines flagged 'TBD' |  |  | Count and $ exposure
AUDIT CONCLUSION
If all PASS/FAIL checks above show PASS, the workbook is internally consistent: (1) hard-cost grand total sums detail rows only; (2) soft-cost grand total sums detail rows only; (3) subtotal rows independently sum to the same total — proof of no double-counting; (4) GC fee and contingency mechanics tie correctly to Assumptions drivers; (5) per-sq.-ft. cost lands within a defensible band of the Ottawa premium custom benchmark. Soft checks (8 and 9) are reasonableness checks; small variances are expected pre-tender.