## Cover
ENGAGEMENT REPORT · REAL ESTATE DEVELOPMENT ADVISORY
Small-Scale Infill Residential Development
Development Pro-Forma · Planning · CMHC Financing
Anonymised case study · two-building infill, Ottawa, Ontario
Prepared by Lumenalis Consulting Ltd.
PROJECT PROFILE
Asset type | Two detached triplexes — purpose-built rental
Programme | 6 dwellings (each building: 1 principal dwelling + 2 additional dwelling units)
Location | Established, transit-oriented Ottawa neighbourhood (address withheld)
Site | Severed corner lot subdivided into two parcels
Financing strategy | CMHC MLI Select construction-to-takeout (energy + affordability tiers)
Planning status | Severance + minor variances — appeal allowed by the Ontario Land Tribunal (2024)
HEADLINE OUTPUTS
Total project cost (rebuilt budget) |  | 3999347
Total dwellings |  | 6
Cost per dwelling |  | 666558
Cost per sq ft GBA |  | 727
Stabilised net operating income (CMHC) |  | 211134
Applied capitalisation rate |  | 5%
CMHC estimated value (stabilised) |  | 4222688
CMHC first mortgage |  | 3320000
First-mortgage rate / amortisation |  | 3.95% · 40 yr
Debt-service coverage ratio |  | 1.28
Document control no. | LUM-RP-RES02-01.00
Version / date | v1.0 · 2026-05-21
Anonymised for publication: address, postal code, ownership, counsel, tribunal-member and consultant names, and file/board numbers removed (PIPEDA, S.C. 2000, c.5). All figures are those of the underlying engagement. Two cost lenses appear — the rebuilt development budget (cost-to-build) and the CMHC underwriting (operating value & financing); each is shown in its own tab and reconciled on Sources & Method.

## Summary
Pro-Forma Summary — Total Project Cost
Cost Category | Restated ($) | % of TPC | Source link
HARD COSTS
Construction hard costs (Hard_Costs tab)
(HST on inputs handled via ITCs — see HST_Analysis tab) | 0
HARD COST SUBTOTAL
SOFT COSTS
Design / engineering / permits (Soft_Costs tab)
(HST on inputs handled via ITCs — see HST_Analysis tab) | 0
SOFT COST SUBTOTAL
LAND & DEV CHARGES
Land acquisition + LTT + title
Development charges + parkland + EDC
LAND & DEV CHARGES SUBTOTAL
FINANCING
Construction interest + commitment + admin + refi
Builders' risk insurance (already in hard) — no double-count | 0
FINANCING SUBTOTAL
MANAGEMENT & SUPERVISION
PM/PC fee on hard+soft
Site supervision fee on hard+soft
Corporate overhead allocation
CONTINGENCY
Scope + escalation + soft + owner reserve
HST (SELF-SUPPLY, SELECTED SCENARIO)
Net self-supply HST burden (Scenario from Assumptions!C60)
TOTAL PROJECT COST (TPC)
Variance vs source ($4,008,500)
TPC per unit
TPC per sqft GBA
Hard cost per sqft GBA
Soft-to-hard ratio
Note on C7: Comment: Construction-input HST is recoverable via ITCs under Scenarios A/B; no separate hard-cost allocation. Scenario C captures unrecoverable input HST in the HST line below. by Claude
Note on C28: Comment: Reflects gross HST on FMV less applicable rebate (NRRP or PBRH). ITCs on construction-period inputs are presumed recovered separately and are NOT added back here unless Scenario C is selected. by Claude

## Assumptions
Assumptions — change the shaded input values; all other tabs recompute
PROGRAM
Number of buildings | 2
Units per building | 3
Total units
GBA per building (sqft) | 2750
Total GBA (sqft)
Average unit size NSF (sqft) | 800
MARKET COST RATES (Ottawa Q2 2026)
Hard cost target $/sqft GBA | 315
Soft cost loading factor (% of hard) | 13%
Scope contingency on hard costs | 10%
Escalation reserve (annualized) | 4%
Construction duration (months) | 14
Owner reserve (% of hard+soft) | 3%
LAND & ACQUISITION
Land purchase price ($) | 1070000
Land transfer tax (Ontario marginal)
Legal — acquisition | 4500
Severance legal carryover | 4000
OLT legal / appeal | 14900
Title insurance / disbursements | 1800
MUNICIPAL FEES (City of Ottawa 2025 schedule)
Building permit base + per-m² ($)
7% admin surcharge on permit
Plumbing & drainage permit ($) | 1400
HVAC / mechanical permit ($) | 700
Zoning compliance / lot grading review ($) | 1500
Demolition permit ($) | 425
Road occupancy / encroachment ($) | 3500
Water/sewer connection (per service) | 5800
Hydro Ottawa connection | 2500
Gas service activation (Enbridge) | 800
DEVELOPMENT CHARGES (Ottawa 2026 schedule, after exemptions & credits)
Total City DC payable (net of credits & ARU exemptions) | 50000
CILP per dedicating dwelling (main dwelling only; ADUs exempt) | 20000
OCDSB Education DC per unit | 1373
OCCDSB Education DC per unit | 0
INTERMEDIATE COMPUTATION — Ontario LTT
Marginal LTT on $1.07M ($55k×.5% + $195k×1% + $150k×1.5% + balance×2%)
FINANCING
Construction loan rate (annualized) | 7.25%
Average draw utilization (%) | 55%
Commitment fees (% of loan) | 0.75%
Lender legal / appraisal / QS / inspections | 18500
Post-construction refinance fee (% of takeout) | 2%
Construction loan size (max)
HST / NRRP / PBRH
HST rate (Ontario) | 13%
FMV per unit on substantial completion ($) | 350000
HST scenario selector (A / B / C) | A
GENERAL
PM/PC fee on hard+soft | 4%
Site supervision fee on hard+soft | 4%
Corporate overhead allocation | 0.5%
Note on C6: Assumed 3-per-building multiplex consistent with hard-cost ratios in source (HRV $21K/6 = $3.5K/unit; plumbing $60K/6 = $10K/unit; cabinets $60K/6 = $10K/unit). Adjust if confirmed unit count differs.
Note on C8: Derived from siding $125K @ ~$22/sqft of wall area implying ~5,700 sqft wall; consistent with two 3-storey buildings of ~2,750 sqft GBA each.
Note on C13: Altus Group Canadian Cost Guide 2025/26 — Ottawa low-rise wood-frame multi-residential, mid-range finishes with OBC SB-12 / MLI Select envelope (R-31 walls, R-60 roof, triple-glazed windows): $285–$345/sqft. Midpoint used.
Note on C14: BTY Group Q4-2025 Market Intelligence: 12–18% typical soft load on small/medium urban infill. 13% reflects shared design across two near-identical buildings.
Note on C15: AACE International Recommended Practice 18R-97 Class-3 estimate (design 30–70% complete) implies +10/-5% contingency range; 10% is centerline.
Note on C16: StatCan Building Construction Price Index Ottawa CMA 2024Q4 YoY: +3.8%; rounded to 4% to cover labour-rate creep through 18-month build.
Note on C18: Discretionary owner reserve for change orders / scope creep / interest cushion. Best-practice 2–5% (PMI Construction Extension to PMBOK 7th ed., 2022).
Note on C21: Carried over from source (already executed).
Note on C26: Stewart/FCT residential title insurance for $1.07M property ~$1,500–$2,000.
Note on C31: Ottawa Plumbing Permit fee schedule 2025 — per fixture × ~50 fixtures across 6 units.
Note on C34: Ottawa demolition permit flat fee + admin.
Note on C35: Required for sidewalk closure, hoist setup, lay-down area; ~14 months at posted rates.
Note on C36: Ottawa Water Connection Charges By-law 2019-394, two services × ~$2,900.
Note on C37: As per source — typical residential connection deposit.
Note on C38: Two services × $400 activation.
Note on C41: User-calibrated to ~$45-50K total based on 658 Somerset West comparable. Reflects: (a) DC Act s.2(3.2) Additional Residential Unit exemption per Bill 23 (More Homes Built Faster Act 2022) — up to 3 ARUs in a new build are exempt; (b) demolition credit for the existing single-family dwelling on site; (c) Ottawa DC By-law 2024-179 as amended by April 1, 2026 3.6% BCPI-tied schedule (avg 1% decrease inside Greenbelt); (d) Bill 17 payment timing at first occupancy permit, interest-free 18-mo deferral. Verify exact net payable at building permit issuance via City Finance DC calculator.
Note on C42: $20K per FREEHOLD MAIN DWELLING. Configuration: each building is a freehold triplex = 1 main dwelling + 2 Additional Dwelling Units (ADUs). Under Planning Act s.42(1.3-1.5) as amended by Bill 23 (More Homes Built Faster Act 2022), ADUs in a residential building are EXEMPT from parkland dedication/cash-in-lieu. Therefore the dedicating dwelling count equals the number of buildings (2), not the total unit count (6). 2 × $20K = $40K total CILP. Same statutory logic underpins the DC reduction on this site.
Note on C43: OCDSB EDC By-law 2024 — apartment >700 sqft rate.
Note on C44: OCCDSB does not levy EDC in Ottawa as of 2024 (only OCDSB).
Note on C50: CMHC-insured construction take-out rates Apr-2026 BoC overnight +175 bps spread; Bank of Canada Bank Rate 5.00% as of Apr-2026.
Note on C51: Industry rule of thumb: peak draw utilization profile averages ~55% over the build.
Note on C54: CMHC application + premium pass-through. NOTE: CMHC MLI Select premium is funded into mortgage.
Note on C58: Federal 5% + Ontario 8% combined HST.
Note on C59: Self-supply fair-market value per Excise Tax Act s.191(3). CRA RC4231 specifies FMV excludes HST payable on the FMV itself. $350K is the federal NRRP phase-out start — at exactly this FMV the federal rebate is at its $6,300/unit cap; any FMV uplift erodes the federal rebate linearly to zero at $450K. Revisit with appraisal at substantial completion.
Note on C60: A = Standard NRRP rebate (default — defensible base case). B = PBRH rebate (post-Sept 2023 starts, qualifying MURC only — net HST = $0 if eligible). C = Punitive: standard NRRP + unrecovered construction-input HST (use only if tax accountant confirms no ITC claim on inputs). Change this letter in cell C60 to flex the Summary HST line.

## Planning & Approvals
Planning & Approvals
Land-use approval pathway secured for the development (anonymised).
APPROVAL OBTAINED
Instruments | Consent (severance) under s. 53 of the Planning Act, plus minor variances under s. 45 — to subdivide one corner lot into two parcels and permit two detached triplexes (six dwellings total).
Pathway | Applications refused by the municipal Committee of Adjustment; refusal appealed to the Ontario Land Tribunal (OLT); appeal heard by video (August 2024); decision issued September 2024.
Outcome | Appeal ALLOWED. Provisional consent granted and the zoning variances authorised, subject to nine conditions.
Variances authorised | Reduced lot widths of approx. 16.3 m and 11.2 m (vs. an 18 m minimum), and a parking reduction from one space to zero on one lot — offset by a second space on the adjoining lot to preserve a mature tree and the 40% canopy requirement.
PLANNING RATIONALE
Policy basis | Found consistent with the Provincial Policy Statement (2020); conforms to the City Official Plan and the applicable secondary plan.
Intensification context | Site within an Official Plan 'Evolving Neighbourhood Overlay' in the Outer Urban Transect, zoned first-density residential (permitting additional dwelling units) — a context the Plan identifies for transit-supportive infill.
Transit orientation | Within roughly 400 m of a rapid-transit station and walking distance of a university campus; a second post-secondary campus is a short transit ride away. The development thesis is purpose-built student-oriented rental with low private-vehicle demand.
Four-test analysis | The variances were found to maintain the general intent of the Official Plan and Zoning By-law, to be desirable and appropriate, and to be minor in nature; the consent met the applicable tests under ss. 51(24) and 53 of the Act.
CONDITIONS OF APPROVAL (NINE)
Condition 1 | Cash-in-lieu of parkland dedication (municipal by-law, with appraisal).
Condition 2 | Tree-planting plan — one new tree per lot to enhance canopy and streetscape.
Condition 3 | Removal of the existing dwelling confirmed in writing.
Condition 4 | Independent water, sanitary and storm connections for each parcel, not crossing the severance line.
Condition 5 | Stormwater management brief by a licensed civil engineer (peak-flow control to the 100-year storm).
Condition 6 | Development agreement registered on title; environmental compliance approval if required.
Condition 7 | Grading and drainage plan for both severed and retained parcels.
Condition 8 | Conveyance of a 3 m × 3 m corner sight triangle to the municipality.
Condition 9 | Development agreement for an asphalt overlay if servicing requires three or more pavement cuts; plus a noise covenant for the adjacent arterial road.
Source: Ontario Land Tribunal decision and order (2024), anonymised. Parties, counsel, the presiding member, the address and all file numbers have been removed. The planning facts are reproduced for context; this is not legal advice.

## Hard_Costs
Hard Construction Costs — Restated against Ottawa Q2-2026 unit rates
Cost Center | Original ($) | Restated ($) | Variance ($) | Variance % | Unit Driver | Basis / Source
SITE PREP & DEMOLITION
Site prep, signage, fencing, hoarding | 7500 | 9500 |  |  | fixed | Two-site fencing 14 mo. + 30A hoist power + temp toilets; AGC of Ontario 2025 rate sheet.
House demolition | 18500 | 22500 |  |  | fixed | Existing 2-storey + slab; +20% vs source given hazmat designated-substances survey now mandatory (O.Reg 278/05).
Bush / vegetation clearing | 700 | 700 |  |  | fixed | As per source.
Shed demolition | 500 | 500 |  |  | fixed | As per source.
Demo cleanup / misc | 2500 | 3000 |  |  | fixed | Modest uplift for two-building site coordination.
Construction bins (14 mo.) | 8400 | 11200 |  |  | fixed | Tomlinson 2026 rate: $800/swap × 14 swaps over 14-mo build.
Designated Substances Survey + abatement allowance | 0 | 4500 |  |  | fixed | REQUIRED under O.Reg 278/05 prior to demolition — missing from source.
Excavation, backfill, trenching, dewatering | 97350 | 105000 |  |  | fixed | +8% for dewatering allowance (high water-table risk per geotechnical report).
Soil testing — foundation bearing | 1000 | 1500 |  |  | fixed | Two footprints, two test sets.
Subtotal — SITE PREP & DEMOLITION
STRUCTURE & ENVELOPE
Foundation (concrete + waterproofing) | 80000 | 88000 |  |  | $/sqft footprint | $48/sqft of footprint × ~1,830 sqft; +10% for hydrostatic damp-proofing required by OBC 9.13.3.3.
Framing labour | 51500 | 62000 |  |  | $/sqft GBA | $11.25/sqft GBA × 5,500 sqft. Source under-prices labour vs Ottawa carpentry COLA 2025 (+8.7% YoY, ICI Settlements Bulletin).
Framing material (incl trusses & engineered I-joists) | 138000 | 152000 |  |  | $/sqft GBA | $27.6/sqft. Random Lengths Composite Index Q2-2026 ~+10% vs 2025.
Staircases (manufactured) | 15000 | 16500 |  |  | per stair | $2,750 × 6 stair runs (one per unit if stacked townhouse layout).
Roofing (asphalt shingle + ice/water) | 36000 | 39000 |  |  | $/sqft roof | $13/sqft × ~3,000 sqft roof area (steeper pitch & longer eaves typical of multiplex).
Eavestroughs + downspouts + storm tie-in | 7000 | 8500 |  |  | fixed | Storm tie-in to municipal lead at curb — source under-estimated.
Windows (triple-glazed, Argon, U≤1.05) | 82800 | 96000 |  |  | per unit | MLI Select envelope requires U≤1.05 — premium window upgrade adds ~16%.
Exterior doors (insulated steel + sidelights) | 12000 | 13000 |  |  | per door
Siding system (Hardie panel + soffit + fascia) | 125000 | 140000 |  |  | $/sqft wall | $24/sqft wall × ~5,800 sqft wall area; James Hardie 2026 distributor price list.
Parging + foundation coating | 7800 | 8500 |  |  | fixed
Subtotal — STRUCTURE & ENVELOPE
MECHANICAL / ELECTRICAL / PLUMBING
HVAC equipment + ducting (gas-fired or HP) | 54000 | 60000 |  |  | per unit | $10K/unit × 6 = MLI Select compliant; consider air-source heat pump premium $+2K/unit.
HRV (mandatory under SB-12 / MLI Select) | 21000 | 22500 |  |  | per unit
HVAC misc / commissioning | 6500 | 8000 |  |  | fixed | NRCAN H2K commissioning + EnerGuide blower-door test (mandatory for MLI Select Tier-2 rebate).
Plumbing rough-in labour | 60000 | 66000 |  |  | per fixture | $1,200/fixture × ~55 fixtures (kitchen, 2 bath per unit avg).
Plumbing service & main | 18000 | 20000 |  |  | fixed
Plumbing fixtures (mid-grade) | 16500 | 18000 |  |  | per unit
Irrigation contractor | 7500 | 7500 |  |  | fixed | Optional — flag for value engineering.
Electrical general contractor | 66000 | 72000 |  |  | per unit | $12K/unit; ESA 2025 inspection fees included.
Electrical fixtures | 7200 | 8400 |  |  | per unit
Electrical service entry & meter base | 25000 | 28000 |  |  | fixed | 200A service per building × 2 buildings; Hydro Ottawa connection deposit separate.
Smart-home / data rough-in (Cat-6A + WAP backbone) | 6000 | 7500 |  |  | fixed
Internet finishing (patch panels, jacks) | 2500 | 3000 |  |  | fixed
Security/camera system (2 entries × DVR) | 3000 | 4200 |  |  | fixed | Insurance discount eligibility — recommend upgrade.
Subtotal — MECHANICAL / ELECTRICAL / PLUMBING
INTERIORS & FINISHES
Insulation — base (R-31 walls / R-60 attic) | 64750 | 72000 |  |  | $/sqft GBA | MLI Select requires improved envelope; bumped to R-31/R-60.
Insulation — spray-foam basement (CCMC 14140-L) per Building B plan | 15250 | 17500 |  |  | fixed | Closed-cell spray-foam per Building B specification.
Drywall | 45000 | 50000 |  |  | $/sqft GBA
Plaster / Level-5 finish allowance | 39000 | 41000 |  |  | fixed
Drywall extras / patching | 10000 | 12000 |  |  | fixed
Painting | 25000 | 30000 |  |  | per unit | $5K/unit; original missing 'painting extras' line item.
Flooring — material (engineered hardwood + LVT) | 25500 | 30000 |  |  | $/sqft
Flooring — labour | 10500 | 12000 |  |  | $/sqft
Transitions + reducers | 5000 | 5000 |  |  | fixed
Flooring extras / damage allowance | 15000 | 15000 |  |  | fixed
Bathroom tile — material | 10800 | 12000 |  |  | per bath | $1K/bath × 12 baths (2 per unit avg).
Bathroom tile — labour | 14000 | 15500 |  |  | per bath
Backsplash kitchen tile | 3000 | 3600 |  |  | per unit
Bathroom extras | 6000 | 7000 |  |  | per unit
Shower glass material | 7200 | 8400 |  |  | per shower
Shower kit labour | 3600 | 4200 |  |  | per shower
Cabinets — kitchen + bath | 60000 | 66000 |  |  | per unit | $11K/unit; mid-range custom plus appliance garage etc.
Countertops (quartz) | 48000 | 54000 |  |  | per unit | $9K/unit; 35 sqft of quartz/unit at $145/sqft installed.
Trim & doors — material + hardware | 36000 | 39000 |  |  | $/sqft GBA
Trim & doors — labour | 9000 | 10500 |  |  | fixed
Bathroom hardware | 4500 | 5400 |  |  | per bath
Misc hardware | 1500 | 1800 |  |  | fixed
Subtotal — INTERIORS & FINISHES
EXTERIOR / SITE WORKS
Asphalt driveway / walkways | 11500 | 13000 |  |  | $/sqft
Landscape labour | 15000 | 17000 |  |  | fixed
Landscape material (sod, trees per arborist plan) | 24500 | 28000 |  |  | fixed | Required tree replacements per Ottawa Tree Protection By-law 2020-340 + arborist report.
Subtotal — EXTERIOR / SITE WORKS
APPLIANCES & FF&E
Appliances | 27000 | 30000 |  |  | per unit | $5K/unit × 6 units.
Appliance install extras | 2000 | 2400 |  |  | fixed
Furniture (model unit + common areas) | 18000 | 18000 |  |  | fixed | Optional — only required if marketing model unit.
Subtotal — APPLIANCES & FF&E
SITE OVERHEAD / CONSTRUCTION SUPPORT
Site cleaning ongoing | 2500 | 3500 |  |  | fixed
Final cleaning (turnover) | 3200 | 3600 |  |  | fixed
Safety overhead (PPE, signage, training) | 1500 | 2500 |  |  | fixed | Ministry of Labour O.Reg 213/91 compliance — under-budgeted at $1.5K.
Plan printing / drawing reproduction | 500 | 500 |  |  | fixed
Fence depreciation | 500 | 750 |  |  | fixed
Construction signage | 1000 | 1000 |  |  | fixed
Drone footage / progress photography | 750 | 750 |  |  | fixed
Builders' risk insurance (course-of-construction) | 9800 | 12500 |  |  | % TPC | $2.0–$2.5/$1,000 of TPC; 14-mo policy on ~$3M hard+soft.
Heating equipment rental (temporary heat) | 2500 | 4500 |  |  | fixed | Two 14-mo builds in Ottawa winter = significant temp heat load.
Tool / equipment rental allowance | 2500 | 3000 |  |  | fixed
Site PM labour buffer | 18500 | 20000 |  |  | fixed
Equipment rentals (mini-ex, lifts) | 6000 | 7000 |  |  | fixed
Misc material allowance | 7500 | 8500 |  |  | fixed
Misc safety items | 1500 | 1800 |  |  | fixed
Boards & signage | 1200 | 1200 |  |  | fixed
Subtotal — SITE OVERHEAD / CONSTRUCTION SUPPORT
TOTAL HARD COSTS
Restated $/sqft GBA
Restated $ per unit

## Soft_Costs
Soft Costs — Design, Engineering, Approvals, Permits
Cost Center | Original ($) | Restated ($) | Variance ($) | Basis / Source
DESIGN & PROFESSIONAL
OLT architectural fees (carryover) | 15500 | 15500 |  | Already incurred / contracted; held at source.
Architectural SD + DD | 9000 | 11000 |  | Two-building variation requires duplicated detailing; +22% premium typical for split lot.
Architectural CD | 14000 | 16500 |  | Construction documents for two buildings.
Architectural site visits / CA | 4500 | 6000 |  | OAA recommended Construction Administration scope minimum — 14-mo build.
Structural engineering | 4500 | 6500 |  | Per stamped structural drawings — fee likely understated for two buildings.
Mechanical engineering | 4500 | 5500
Electrical engineering | 2500 | 3500
Plumbing engineering (delegated design) | 0 | 2500 |  | Missing from source — required for >5 fixture units to OBC.
Geotechnical engineering | 9500 | 9500 |  | As per source — already engaged.
Grading engineering | 10500 | 10500
Energy modeling for MLI (NRCAN H2K — 2 models for Bldg B, 1+ per Bldg A) | 4500 | 7500 |  | Per plan notes: multiple H2K energy models for Building B and Building A.
Arborist + tree protection plan | 1650 | 2200 |  | Ottawa By-law 2020-340 tree replacement plan required.
ESA Phase 1 (if needed) | 3500 | 3500 |  | Retained as contingency line.
Quantity surveyor (CMHC requirement) | 11250 | 13500 |  | MLI Select demands cost certificates at each draw — typical Altus/Turner & Townsend retainer for 6-unit project.
Transportation impact (TIR) study | 400 | 400
OLT lawyer | 14900 | 14900
COA / planning legal | 4500 | 4500
Severance legal carryover | 4000 | 4000
Severance closing & survey | 13500 | 13500
Survey of record | 4500 | 4500
Misc consultants | 3500 | 5000
Subtotal — DESIGN & PROFESSIONAL
MUNICIPAL PERMITS & FEES
Building permit + 7% surcharge |  |  |  | Linked to Assumptions B29/B30.
Plumbing & drainage permit | 0 |  |  | Missing from source.
HVAC / mechanical permit | 0 |  |  | Missing from source.
Zoning compliance review | 0 |  |  | Missing from source.
Demolition permit | 0 |  |  | Missing from source.
Road occupancy / encroachment | 0 |  |  | Missing from source.
Water / sewer connection fees | 0 |  |  | Missing from source.
Hydro Ottawa connection | 2500
Gas service activation (Enbridge) | 0 |  |  | Missing from source.
Subtotal — MUNICIPAL PERMITS & FEES
SUPERVISION & MANAGEMENT (built up in Summary)
Note: PM/PC, supervision, overhead computed on % of hard+soft — see Summary tab |  |  |  | Cross-reference only.
TOTAL SOFT COSTS (ex-management)

## Land_DevCharges
Land Acquisition & Development Charges
Item | Original ($) | Restated ($) | Basis
LAND
Land purchase | 1070000 |  | Held at source — acquired prior to budgeting.
Ontario LTT (corrected) | 8500 |  | Source $8,500 understated. Statutory marginal rate on $1,070,000 = $17,875 (LTT Act R.S.O. 1990 c.L.6 s.2(1)). Variance vs source: +$9,375.
Title insurance + disbursements | 0 |  | Not separately budgeted in source.
Subtotal — LAND
DEVELOPMENT CHARGES & PARKLAND
Ottawa DC — total payable (net of exemptions & credits) | 44500 |  | User-calibrated $50K total reflecting Bill 23 ARU exemption (DC Act s.2(3.2)), demolition credit for existing dwelling, and Ottawa 2026 schedule (eff. Apr 1, 2026; 3.6% BCPI-tied; avg -1% inside Greenbelt). a comparable Ottawa site comparable: 2 ADUs added to existing 21-unit building were essentially exempt under same statutory framework.
Cash-in-lieu of parkland (buildings × $20K/main dwelling) | 19000 |  | 2 freehold triplexes × $20K each = $40K total. ADUs (2 per building = 4 ADUs total) are exempt from parkland dedication under Planning Act s.42(1.3-1.5) as amended by Bill 23. Dedicating count = number of main dwellings = number of buildings, not total units.
OCDSB Education DC (main dwellings only; ADUs exempt) | 19500 |  | 2 main dwellings × $1,373 = $2,746. ADUs are exempt from Education DCs under Education Act s.257.54 as amended by Bill 23, paralleling the DC exemption. Source $19,500 over-stated.
Subtotal — DEVELOPMENT CHARGES & PARKLAND
TOTAL LAND & DEV CHARGES

## Contingencies
Contingency Decomposition (replaces $375,000 lump sum)
Source budget bundles $350K construction + $25K soft contingency. Best practice (AACE 18R-97; PMI 2022) decomposes by risk category.
Component | % Rate | Amount ($) | Justification
Scope contingency (% of hard) |  |  | AACE 18R-97 Class-3 estimate band ±10%
Escalation reserve (annualized × build months / 12) |  |  | StatCan BCPI Ottawa CMA 2024Q4 trend
Soft cost contingency (5% of soft) | 5% |  | Smaller exposure on procured services / fixed fees
Owner reserve (% of hard+soft) |  |  | Owner discretion change orders; PMI Construction Extension 2022
TOTAL CONTINGENCY
Source budget contingency (construction $350K + soft $25K) |  | 375000
Variance vs source

## Financing
Construction Financing Model
Inputs (linked to Assumptions)
Construction loan size
Annualized rate
Build duration (months)
Average draw utilization
Commitment fee rate
Refinance fee on takeout
Outputs
Construction interest reserve
Commitment fees
Lender legal / appraisal / QS / inspections
Admin / misc | 4500
Post-construction refinance fee (CMHC MLI premium)
TOTAL FINANCING COST
Source budget financing (interest + commitment + admin + refi + adj) | 387500
Variance ($)
Note on C5: 85% of TPC — conservative MLI Select construction LTC.
Note on C13: Comment: Interest reserve = Loan × Rate × (Months/12) × AvgUtilization. Standard underwriting method per CMHC MLI Select Construction Financing Guidelines 2024. by Claude
Note on C17: Comment: CMHC MLI Select insurance premium passed into takeout. Actual premium = 1.75–5.50% depending on score points achieved. Using 2.0% as midpoint placeholder. by Claude

## HST_Analysis
HST Self-Supply Analysis — Three Scenarios (NRRP / PBRH / Unrecovered ITCs)
Self-supply at substantial completion triggers HST on FMV of the residential complex per ETA s.191(3). Rebate mechanics depend on whether the project qualifies for the Purpose-Built Rental Housing rebate (PBRH, post-Sept 13 2023 starts, qualifying multiple-unit residential complex) or only the standard New Residential Rental Property rebate (NRRP). ITCs on construction-period inputs are a SEPARATE question — recoverable if the entity is a registrant and inputs are tied to the self-supply taxable event, NOT to the post-self-supply exempt rental use. The PBRH/NRRP determination is worth ~$109K under the current FMV assumption.
INPUTS (linked to Assumptions)
FMV per unit (excl HST on FMV per CRA RC4231)
Total units
Total deemed FMV
HST rate (federal 5% + Ontario 8%)
Gross self-supply HST
SCENARIO A — Standard NRRP rebate (defensible base case)
Federal NRRP per unit (36% × 5% × FMV; $6,300 cap at FMV ≤ $350K; phased to $0 at $450K)
Ontario NRRP per unit (75% × 8% × FMV, $24,000 cap)
Total NRRP per unit (A)
Total NRRP rebate across units (A)
NET self-supply HST burden — Scenario A
SCENARIO B — PBRH rebate (if qualifying MURC, not disqualified triplex)
Federal PBRH rebate (100% of 5% federal HST, no cap)
Ontario PBRH rebate (100% of 8% provincial HST, no cap)
Total PBRH rebate
NET self-supply HST burden — Scenario B
SCENARIO C — Punitive: standard NRRP + unrecovered construction-input HST
Unrecovered construction-input HST (13% on hard+soft, no ITC claim)
Plus: net self-supply HST after standard NRRP (= Scenario A)
TOTAL HST drag — Scenario C
SELECTED SCENARIO (input letter at Assumptions!C60)
Scenario in use
Selected NET HST burden (flows to Summary as project cost line)
Critical eligibility question (worth ~$109,200)
PBRH is unavailable for condos, single-unit, duplexes, and triplexes per CRA Guide 19-3-9. Each building here is a freehold triplex (1 main + 2 ADUs). Two possible CRA parsings: (a) two disqualified triplexes → Scenario A applies, net HST burden = $109,200; (b) one integrated six-unit MURC → Scenario B may apply, net HST burden = $0. Tax counsel determination required. Until confirmed, default to Scenario A.
ITC treatment of construction-period inputs
If entity is GST/HST registrant constructing new housing for self-supply, ITCs may be claimed on construction-period inputs (CRA: 'GST/HST and home construction'). After self-supply, no further ITCs because long-term rental is exempt. Scenarios A and B assume ITCs are claimable and construction-input HST is recovered. Scenario C assumes input HST is unrecoverable — use only if tax counsel confirms.
Note on C14: Comment: ETA s.256.2(3); CRA RC4231. At exactly $350K FMV, federal NRRP = $6,300/unit (cap binding). by Claude
Note on C15: Comment: Ontario NRRP — Taxation Act 2007 S.O. 2007 c.11 Sch.A s.103. At $350K FMV: 75% × $28K = $21,000. by Claude
Note on C21: Comment: ETA s.256.2.1 — Federal PBRH at 100% of federal HST. Eligibility (CRA Guide 19-3-9): construction begins after Sept 13 2023 and before 2031; substantial completion before 2036; qualifying multiple-unit residential complex. EXCLUDED: condos, single-unit, duplexes, triplexes, leased-land/trailer-park housing. Two-triplex configuration likely disqualifies UNLESS treated as one integrated six-unit MURC. Tax counsel determination required. by Claude
Note on C22: Comment: Ontario provincial PBRH mirrors federal — 100% of provincial HST. Conditional on federal PBRH eligibility. by Claude
Note on C27: Comment: Applies ONLY if entity is NOT a GST/HST registrant, OR tax accountant determines inputs are tied to exempt rental use rather than the taxable self-supply. Confirm with tax counsel before relying on this scenario as base case. by Claude

## Operating Pro-Forma
Stabilised Operating Pro-Forma
CMHC MLI Select underwriting basis — stabilised year-one operations.
REVENUE
Component | Basis | Units | Rent / mo | Annual
Residential — 4-bedroom suites | 1,049 SF avg · $3.72/SF | 6 | 3900 | 280800
Parking | 2 stalls | 2 | 87.5 | 4200
Gross potential revenue
Less: vacancy & bad debt (3.0%) | submarket 4-yr avg ~1.15%
Effective gross revenue
OPERATING EXPENSES
Expense | Basis |  | % EGR | Per unit / Annual
Property taxes | Per appraisal |  | 5.79% | 16002
Insurance | Per appraisal |  | 1.25% | 3450
Internet | Per appraisal |  | 0.76% | 2100
Utilities | Per appraisal |  | 6.51% | 18000
Repairs & maintenance | CMHC wood benchmark (ON) |  | 1.8% | 4980
Salaries | CMHC wood benchmark (ON) |  | 1.2% | 3330
Management | CMHC wood benchmark (ON) |  | 4.25% | 11749
Other costs | CMHC wood benchmark (ON) |  | 1% | 2765
Reserve (5 appliances + heat pump) | CMHC wood benchmark (ON) |  | 1.06% | 2940
Total operating expenses
NET OPERATING INCOME & VALUE
Net operating income (NOI)
Applied capitalisation rate |  |  |  | 5%
CMHC estimated value (stabilised) |  |  |  | 4222688
Value per residential unit |  |  |  | 703781
Breakeven rent per suite / month |  |  |  | 3580
Default point |  |  |  | 93.25%
NOI shown is the CMHC MLI Select underwriting estimate (stabilised year one). Value is NOI capitalised at 5.0%. Operating-expense benchmarks follow the CMHC Ontario wood-frame standard; taxes, insurance, internet and utilities are per appraisal.

## CMHC Financing & Value
CMHC Financing & Value
MLI Select first-mortgage sizing, insurance premia and coverage.
FIRST MORTGAGE |  | CMHC FEES
Loan amount | 3320000 | Net loan amount | 3320000
Loan-to-cost | 95% | Application fee | 1200
Loan-to-value | 78.62% | CMHC premium (7.00%) | 232400
Interest rate | 3.95% | Amortisation premium (0.75%) | 24900
Amortisation | 40 years | Sub-total premia | 257300
Term | 5 years | MLI Select discount (10%) | -25730
Annual debt service | 164478 | Total CMHC fees | 232770
Cash flow after debt service | 46657 | Gross CMHC loan (incl. fees) | 3552770
Debt-service coverage ratio | 1.28
Debt yield | 6.36%
Loan per net sq ft | 527.49
Loan per suite | 553333
CMHC COST & VALUE SUMMARY
Metric | Value | Metric | Value
Land value | 1070000 | Net leasable area | 6294
Total hard cost | 1643000 | Average unit size | 1049
Total soft cost | 537000 | Number of units | 6
Total contingency | 92890 | Cost per net sq ft | 556
Total financing cost | 155500 | Cost per suite | 583065
Total construction cost | 3498390 | CMHC estimated value | 4222688
CMHC underwriting view. Note the two cost lenses: this MLI Select submission estimates total construction cost at $3,498,390, whereas the rebuilt development budget (Summary) restates total project cost at $3,999,347. The difference reflects scope and underwriting treatment (e.g. HST self-supply, financing and contingency are stated more fully in the rebuilt budget). Both are retained; see Sources & Method.

## Risk_Register
Risk Register & Sensitivity
Risk ID | Description | Likelihood | Impact ($) | Expected ($) | Mitigation
R-01 | Ottawa DC schedule re-tabled mid-build (Bill 23 unwind ongoing) | 40% | 80000 |  | Lock DC at building permit issuance; budget worst-case schedule.
R-02 | MLI Select scoring shortfall reduces takeout LTV from 95% to 85% | 25% | 250000 |  | Engage CMHC pre-application; cushion equity reserves.
R-03 | Excavation hits unsuitable soils (Leda clay risk in Ottawa) | 20% | 60000 |  | the geotechnical consultant geotechnical Phase 2; pile contingency in scope.
R-04 | Construction labour escalation beyond 4%/yr (ICI Settlements) | 35% | 65000 |  | Lock framing labour via fixed-price subcontract.
R-05 | OBC SB-12 / MLI Select envelope changes during permit review | 25% | 35000 |  | Architect maintains 3 H2K model variants (per Building B plan note).
R-06 | Interest rate exceeds 7.25% modeled — BoC trajectory uncertain | 30% | 45000 |  | Negotiate rate lock at construction loan commitment.
R-07 | Tarion enrollment required if any units sold rather than rented | 20% | 25000 |  | Confirm exit strategy before substantial completion.
R-08 | Hazmat / Designated Substance Survey reveals asbestos in demo | 25% | 28000 |  | Pre-demo DSS (mandatory under O.Reg 278/05) + abatement allowance.
R-09 | Adjacent property damage / underpinning required (infill risk) | 15% | 75000 |  | Builders' risk policy with party-wall extension; pre-construction survey.
R-10 | PBRH ineligibility — two-triplex config disqualifies the federal/Ontario PBRH rebate (only standard NRRP applies) | 60% | 109200 |  | Engage tax counsel pre-occupancy on MURC classification (CRA Guide 19-3-9). Decision worth $109,200 — moves net HST from $0 (Scenario B) to $109,200 (Scenario A).
R-11 | FMV at occupancy exceeds $450K → federal NRRP fully phases out (Scenario A only) | 35% | 37800 |  | Document FMV conservatively at substantial completion; appraisal review.
EXPECTED-VALUE RISK BUDGET
Coverage check: Owner reserve + Soft contingency vs Expected risk
Note on F17: Comment: Positive = contingencies cover expected-value risks. Negative = risk-adjusted exposure exceeds buffer. by Claude

## Sources_Method
Sources & Methodology
Domain | Citation
Cost benchmarks | Altus Group, Canadian Cost Guide 2025/2026 — Ottawa low-rise wood-frame multi-residential.
Cost benchmarks | BTY Group, Market Intelligence Q4-2025 — Ontario residential infill.
Cost escalation | StatCan Building Construction Price Index, Ottawa CMA 2024Q4 (table 18-10-0135-01).
Labour escalation | Ontario ICI Collective Agreements Settlement Bulletin 2025.
Material indices | Random Lengths Composite Index Q2-2026.
Permit rates | City of Ottawa By-law 2014-149 (Building Code Act).
Development charges | City of Ottawa Development Charges By-law (2024-179 as amended; April 1 2026 schedule, 3.6% BCPI-tied, avg -1% inside Greenbelt). User calibration: ~$50K total on this project reflecting ADU exemption + demolition credit.
ADU exemption | Development Charges Act 1997 s.2(3.2); Bill 23 More Homes Built Faster Act 2022.
Parkland | City of Ottawa Parkland Dedication By-law 2022-280; Planning Act R.S.O. 1990 c.P.13 s.42 as amended by Bill 23. ADUs exempt; 2 main dwellings × $20K = $40K.
EDC | Education Act R.S.O. 1990 c.E.2 s.257.54; OCDSB EDC By-law 2024. ADU exemption parallels DC Act.
LTT | Land Transfer Tax Act R.S.O. 1990 c.L.6 s.2(1).
HST self-supply | Excise Tax Act R.S.C. 1985 c.E-15 s.191(3); CRA Guide RC4231.
NRRP rebate | ETA s.256.2; CRA Guide RC4231. Federal 36% × 5%, $6,300/unit cap, phased $350K-$450K. Ontario 75% × 8%, $24,000/unit cap (Taxation Act 2007 s.103).
PBRH rebate | ETA s.256.2.1; CRA Guide 19-3-9. Federal 100% × 5%, no cap. Ontario 100% × 8%, no cap. EXCLUDED: condos, single-unit, duplexes, triplexes. Eligibility starts after Sept 13 2023; substantial completion before 2036.
ITCs on construction inputs | CRA: GST/HST and home construction. Registrants may claim ITCs on construction-period inputs tied to taxable self-supply event; cannot claim ITCs against post-self-supply exempt rental use.
CMHC financing | CMHC MLI Select Program Guide (Feb 2024 revision); CMHC Construction Loan Insurance Guidelines.
Cost-engineering methodology | AACE International Recommended Practice 18R-97 — Cost Estimate Classification System.
Risk methodology | PMI Construction Extension to the PMBOK Guide, 7th edition, 2022.
Building code | Ontario Building Code O.Reg 332/12 (as amended); Supplementary Standard SB-12.
Hazmat | O.Reg 278/05 — Designated Substances in Demolition (OHSA).
Tree protection | City of Ottawa By-law 2020-340 — Tree Protection.
Source budget | Developer source budget, May 2025 (provided).
Comparable project | Comparable Ottawa infill application — two additional dwelling units added to an existing multi-unit building; development charges effectively exempt under DC Act s.2(3.2).
Monday board context | Internal project-management board (reference only).
Methodology notes (cumulative through v2.3)
• | Hard-cost line items restated against Ottawa Q2-2026 unit rates and benchmarked per-sqft GBA or per-unit.
• | Source budget double-counted Architectural Site Visits ($4,500 appears under both Professional Services and Drafting & Architectural Fees); v2.x consolidates to a single $6,000 CA line consistent with OAA recommended scope.
• | Soft costs add five missed lines: plumbing engineering, plumbing/HVAC/zoning/demo permits, road occupancy, water-sewer connection, gas activation, hazmat survey.
• | Ontario LTT recalculated on statutory brackets — source $8,500 understates the $17,875 figure on a $1.07M lot (variance +$9,375).
• | v2.2 update: Ottawa DCs set to $50K flat reflecting Bill 23 ADU exemption (DC Act s.2(3.2)), demolition credit for existing dwelling, and Ottawa April 1 2026 schedule. CILP set per-main-dwelling ($20K) × 2 buildings = $40K because ADUs are statutorily exempt from parkland dedication. OCDSB EDC same dwelling-count basis = 2 × $1,373.
• | v2.3 update: HST model restructured into three scenarios. FMV per unit reset from $480K to $350K. Self-supply at FMV is the core liability per ETA s.191(3); rebate selection (NRRP vs PBRH) determines net cost. Scenario A standard NRRP = $109,200 net (defensible base). Scenario B PBRH = $0 net (only if project qualifies as a single MURC, not two disqualified triplexes per CRA Guide 19-3-9). Scenario C standard NRRP + unrecovered ITCs = $367,151 (punitive; only if no ITC claim).
• | Construction-input HST and self-supply HST are tracked separately. ITCs on inputs are presumed recovered in Scenarios A and B; not recovered in Scenario C.
• | Construction financing rebuilt bottom-up: Loan × Rate × (Months/12) × Average Utilization.
• | Contingency decomposed per AACE 18R-97: scope, escalation, soft, owner reserve.
• | Risk_Register quantifies expected-value exposure; R-10 reflects PBRH ineligibility risk worth ~$109,200; R-11 captures FMV creep above $450K phase-out cliff.
• | Stabilization takeout fees in the source ($27,768.62 with offsetting -$27,768.62) net to zero and are removed.