## Cover
ENGAGEMENT REPORT · REAL ESTATE DEVELOPMENT ADVISORY
Two-Building Mixed-Use Infill
Construction budget, stabilised income pro forma, and CMHC MLI Select underwriting
Purpose-built rental conversion of two adjacent low-rise buildings — 10 residential suites and a ground-floor retail tenancy — in an established inner-urban Ottawa neighbourhood.
Asset class | Mixed-use purpose-built rental (residential and ground-floor retail)
Programme | Two adjacent buildings; 10 residential suites (8 one-bedroom, 2 three-bedroom) plus 730 SF retail
Location | Established inner-urban Ottawa rental submarket (address withheld)
Financing strategy | CMHC MLI Select construction-to-takeout — mixed-use, Tier 3 energy efficiency
Total project cost | $4,198,145
Stabilised net operating income | $223,691 (Year 1)
Status at reporting date | Under construction — 65.4% of total budget committed (41.9% of construction)
Prepared by | Lumenalis Consulting Ltd. — Real Estate Development Advisory
Document control | LUM-RP-MUI-SAMPLE · v1.0 · sanitised public sample
BASIS OF PREPARATION
This sample is built from a live project budget and a CMHC MLI Select underwriting model. All monetary figures are retained from source. The street address, the developer, vendor names, and other identifiers have been removed under the Personal Information Protection and Electronic Documents Act (S.C. 2000, c. 5). Figures are management estimates at the reporting date; they are not an appraisal, and they are not a financing commitment. See the Sources & Method tab.

## Summary
Executive Summary
Two adjacent low-rise buildings converted to a 10-suite residential and ground-floor-retail rental asset, financed under CMHC MLI Select. Figures below are live links to the detail tabs.
PROJECT COST
Total project cost | 4198145.07
Committed to date | 2745973.945
Per cent of budget committed | 65.41%
STABILISED INCOME (YEAR ONE)
Net operating income — residential | 180565.57
Net operating income — commercial | 43126
Net operating income — total | 223691.57
FINANCING — CMHC MLI SELECT
Takeout debt (total) | 3835488
Blended debt-service coverage | 1.186
Cash flow after debt service | 35073.57
RETURNS — MARKET BASIS
Yield on cost | 5.328%
Implied going-in cap rate | 5.231%
Stabilised value at going-in cap | 4260791.8095
Development margin on cost | 1.492%
Equity remaining at takeout | 362657.07
Cash-on-cash on remaining equity | 9.671%
RETURNS — SPONSOR BASIS (FEES RETAINED)
Management fees retained as profit | 340000
Total sponsor profit (incl. retained fees) | 402646.7395
Total sponsor profit margin on cost | 9.591%
KEY JUDGEMENT
On a market basis this reads as a financing-driven hold: the development margin on third-party cost is slim, and the return is manufactured by the takeout — forty-year insured debt recovers about nine-tenths of cost, and the equity that stays in earns a strong cash yield. On a sponsor basis it is stronger, because roughly $340,000 booked as management, supervision, and overhead is paid to the developer and kept as profit, lifting total sponsor profit toward $400,000. The exposures that matter are the takeout rate, the exit cap rate, lease-up of the single retail unit, and the HST treatment of the mixed-use complex.

## Assumptions
Assumptions & Inputs
Values in blue are engagement inputs. Other tabs reference these cells and recompute when they change.
PROGRAMME
Input | Value | Basis / note
Residential suites (no.) | 10 | 8 one-bedroom plus 2 three-bedroom.
One-bedroom suites (no.) | 8 | 371 SF average.
Three-bedroom suites (no.) | 2 | 796 SF average.
Residential rentable area (SF) | 4560 | Net rentable, per underwriting.
Ground-floor retail area (SF) | 730 | Single retail tenancy.
MARKET — RESIDENTIAL RENTS
Input | Value | Basis / note
One-bedroom rent ($/month) | 1900 | Submarket asking, stabilised.
Three-bedroom rent ($/month) | 3000 | Submarket asking, stabilised.
Storage income ($/month) | 100 | Ancillary.
Residential vacancy allowance | 3% | Underwriting; CMHC four-year submarket average near 2.63%.
MARKET — COMMERCIAL
Input | Value | Basis / note
Retail rent ($/SF/year) | 65.75 | Ground-floor retail, net.
Commercial vacancy allowance | 5% | Underwriting.
Commercial operating cost ($/SF) | 3.39 | Structural-vacancy carry on the retail unit.
FINANCING — CMHC MLI SELECT
Input | Value | Basis / note
Mortgage interest rate | 3.9% | MLI Select indicative, construction-to-takeout.
Amortisation (years) | 40 | MLI Select maximum for the qualifying energy tier.
Term (years) | 5 | Initial term.
Residential DSCR floor | 1.1 | MLI Select residential minimum.
Commercial DSCR floor | 1.76 | Underwriting, commercial component.
Residential loan-to-value | 92.4% | MLI Select, energy and affordability tiers.
Commercial loan-to-value | 75% | Mixed-use commercial portion.
VALUATION
Input | Value | Basis / note
Going-in capitalisation rate | 5.25% | Implied by the CMHC lending value; see Returns & Valuation.
Cap-rate sensitivity step (bps) | 0.25% | Applied across the sensitivity grid.
COST
Input | Value | Basis / note
Land acquisition — APS (combined) | 1700000 | Combined purchase of the two properties.

## Budget — Building A
Construction Budget — Building A
Smaller of the two buildings. Trade-package budget with progress (per cent complete) and committed-to-date at the reporting date.
Cost centre / scope item | Budget ($) | % complete | Committed to date ($) | Trade / procurement role
Structural Engineering
Structural Report for project | 1000 | 100% | 1000 | Structural engineer
Structural Design | 4000 | 100% | 4000 | Structural engineer
Geotechnical Exploration | 1000 | 100% | 1000 | Geotechnical / environmental engineer
Subtotal — Structural Engineering | 6000 | 100% | 6000
Plumbing Selections
Plumbing Selections | 6000 | 0% | 0 | General contractor (self-perform)
Subtotal — Plumbing Selections | 6000 | 0% | 0
Furniture selections
Furniture | 12000 | 0% | 0 | General contractor (self-perform)
Subtotal — Furniture selections | 12000 | 0% | 0
Demolition
Demolition Basement | 4000 | 100% | 4000 | General contractor (self-perform)
Basement Abatement for Mould | 5000 | 100% | 5000 | General contractor (self-perform)
Subtotal — Demolition | 9000 | 100% | 9000
Structural wall removal+replacement ground floor
Structural for wall removal+replace | 8000 | 100% | 8000 | General contractor (self-perform)
structural framing for Internal stairs | 3000 | 100% | 3000 | General contractor (self-perform)
structural fix for exterior stairs | 2000 | 100% | 2000 | General contractor (self-perform)
structural fix for balcony second floor | 2000 | 100% | 2000 | General contractor (self-perform)
Framing Shelves for Basement | 1500 | 100% | 1500 | General contractor (self-perform)
Framing Material Order+Budget | 8000 | 100% | 8000 | General contractor (self-perform)
Framing exterior Facade Work | 5000 | 100% | 5000 | General contractor (self-perform)
Framing Addition Labour | 6000 | 100% | 6000 | General contractor (self-perform)
Carpentry labour | 4000 | 100% | 4000 | General contractor (self-perform)
Subtotal — Structural wall removal+replacement ground floor | 39500 | 100% | 39500
Architecture services
Architectural Services | 6300 | 100% | 6300 | Architect
Subtotal — Architecture services | 6300 | 100% | 6300
Electrical
Electrical Rough In Ground Floor | 4000 | 100% | 4000 | Electrical subcontractor
Electrical Rough in Second Floor | 4000 | 100% | 4000 | Electrical subcontractor
Eletrical Rough In Basement | 1000 | 100% | 1000 | Electrical subcontractor
Electrical Finishing | 2000 | 50% | 1000 | Electrical subcontractor
ESA Inspection/report | 100 | 0% | 0 | Electrical subcontractor
Electrical Material Budget | 10000 | 0% | 0 | Electrical subcontractor
Electrical Service | 12000 | 50% | 6000 | Electrical subcontractor
Subtotal — Electrical | 33100 | 48.34% | 16000
Windows
Windows \ | 14000 | 100% | 14000 | Window & door supplier
Exterior doors | 3200 | 100% | 3200 | Window & door supplier
Subtotal — Windows | 17200 | 100% | 17200
Appliances
Appliance budget Item holder | 11000 | 0% | 0 | Appliance supplier
Appliance Install Ground Floor | 500 | 0% | 0 | Appliance supplier
Appliance Install Second FLoor | 500 | 0% | 0 | Appliance supplier
Subtotal — Appliances | 12000 | 0% | 0
Trims and Doors
Doors Installed | 1200 | 0% | 0 | Trim & door installer
Baseboard Installed | 1500 | 0% | 0 | Trim & door installer
Final Trim | 800 | 0% | 0 | Trim & door installer
Recessed Trim Extra | 1000 | 0% | 0 | Trim & door installer
Subtotal — Trims and Doors | 4500 | 0% | 0
Flooring
Subfloor Install | 3000 | 100% | 3000 | General contractor (self-perform)
Flooring for ground floor | 7000 | 0% | 0 | Flooring / tile subcontractor
Flooring second FLoor | 3000 | 0% | 0 | Flooring / tile subcontractor
Flooring Basement | 1500 | 0% | 0 | Flooring / tile subcontractor
Subtotal — Flooring | 14500 | 20.69% | 3000
HVAC
HVAC Rough In | 2000 | 100% | 2000 | HVAC subcontractor
HVAC Primary Install | 5000 | 100% | 5000 | HVAC subcontractor
HVAC Finishing | 2000 | 50% | 1000 | HVAC subcontractor
HVAC testing | 1000 | 0% | 0 | HVAC subcontractor
Material | 5000 | 100% | 5000 | HVAC subcontractor
Subtotal — HVAC | 15000 | 86.67% | 13000
Painting
Primer+First Coat Ground Floor | 1000 | 0% | 0 | Painting subcontractor
Second Coat Ground Floor | 1000 | 0% | 0 | Painting subcontractor
Touch Ups Ground Floor | 500 | 0% | 0 | Painting subcontractor
Primer+First Coat Second FLoor | 1000 | 0% | 0 | Painting subcontractor
Second Coat second floor | 1000 | 0% | 0 | Painting subcontractor
touch ups second floor | 500 | 0% | 0 | Painting subcontractor
Subtotal — Painting | 5000 | 0% | 0
Cleaning
Consruction Cleaning Office | 300 | 0% | 0
Final Cleaning Office | 300 | 0% | 0
Construction cleaning second floor | 300 | 0% | 0
FInal Cleaning Second Floor | 300 | 0% | 0
Subtotal — Cleaning | 1200 | 0% | 0
Cabinets
Cabinet Install | 17000 | 50% | 8500 | Cabinetry supplier
Subtotal — Cabinets | 17000 | 50% | 8500
Countertops
Countertops Install | 10000 | 0% | 0 | Countertop supplier
Countertop Extra | 10000 | 0% | 0 | Countertop supplier
Subtotal — Countertops | 20000 | 0% | 0
Plumbing
Plumbing Rough In Ground Floor | 7500 | 100% | 7500 | Plumbing subcontractor
Plumbing Rough In Second Floor | 7000 | 100% | 7000 | Plumbing subcontractor
Plumbing Finishing | 1000 | 50% | 500 | Plumbing subcontractor
Subtotal — Plumbing | 15500 | 96.77% | 15000
Drywall/Plaster
Drywall Ground Floor | 3000 | 0% | 0 | General contractor (self-perform)
Plaster Ground Floor | 3000 | 0% | 0 | General contractor (self-perform)
Drywall Second Floor | 3000 | 0% | 0 | General contractor (self-perform)
Plaster Second Floor | 4000 | 0% | 0 | General contractor (self-perform)
Subtotal — Drywall/Plaster | 13000 | 0% | 0
Insulation
Ground Floor Exterior Insulation | 7500 | 40% | 3000 | Insulation subcontractor
Second Floor Exterior Insulation | 6000 | 40% | 2400 | Insulation subcontractor
Roof Insulation? | 3000 | 25% | 750 | Insulation subcontractor
Basement Insulation | 3000 | 0% | 0 | Insulation subcontractor
Acoustical insulation | 2000 | 0% | 0 | Insulation subcontractor
Subtotal — Insulation | 21500 | 28.6% | 6150
Inspection Overhead
Framing Inspection | 500 | 100% | 500 | General contractor (self-perform)
Insulation/Firerating Inspection | 500 | 50% | 250 | General contractor (self-perform)
Occupancy Inspection | 500 |  | 0
Subtotal — Inspection Overhead | 1500 | 50% | 750
Management Costs
Management | 23500 | 70% | 16450 | General contractor (self-perform)
Overhead | 8500 | 100% | 8500 | General contractor (self-perform)
Contingency Construction | 20000 | 0% | 0 | General contractor (self-perform)
Supervision | 13500 | 70% | 9450 | General contractor (self-perform)
Subtotal — Management Costs | 65500 | 52.52% | 34400
Facade Materials
Facade Cladding work | 3500 | 0% | 0
Facade Brickwork | 15000 | 0% | 0
Cedar siding | 9000 | 0% | 0
Misc | 3000 | 0% | 0
Subtotal — Facade Materials | 30500 | 0% | 0
Networking
Networking Rough In | 1000 | 50% | 500 | Low-voltage / data subcontractor
Networking Finishing | 2500 | 50% | 1250 | Low-voltage / data subcontractor
Subtotal — Networking | 3500 | 50% | 1750
Contingency
Contingency Budget Minor | 10000 | 0% | 0
Subtotal — Contingency | 10000 | 0% | 0
Helical Piles for rear
Helical piles | 2500 | 100% | 2500 | Helical-pile subcontractor
Helical piles for front | 2000 | 100% | 2000 | Helical-pile subcontractor
Subtotal — Helical Piles for rear | 4500 | 100% | 4500
Glass Partitions Interior
Glass Partitions interior | 7000 | 0% | 0
Subtotal — Glass Partitions Interior | 7000 | 0% | 0
Paving
Paving | 10256 | 0% | 0
Subtotal — Paving | 10256 | 0% | 0
Additional roof front and back
Addition roof front and back | 10000 | 100% | 10000 | Framing subcontractor
Subtotal — Additional roof front and back | 10000 | 100% | 10000
Tenant Compensation
Tenant Compensation | 2955 | 100% | 2955 | Tenant
Subtotal — Tenant Compensation | 2955 | 100% | 2955
Architectural Design
Drafting + Stamping | 7000 | 100% | 7000 | Architectural drafting
Code Consultant Fees | 8500 | 100% | 8500 | Architect (code)
Subtotal — Architectural Design | 15500 | 100% | 15500
Tiles
Tiles | 8500 | 0% | 0 | Flooring / tile subcontractor
Subtotal — Tiles | 8500 | 0% | 0
Professional Services
MEP Full Set Engineering | 10500 | 100% | 10500 | MEP engineer
Drafting Misc | 1200 | 100% | 1200 | MEP engineer
Subtotal — Professional Services | 11700 | 100% | 11700
Insurance
Builder's Insurance | 3450 | 70% | 2415 | Insurance broker
Subtotal — Insurance | 3450 | 70% | 2415
Equipment Rentals
Heating Rentals | 1250 | 80% | 1000
Hand Tool Rental | 785 | 100% | 785
Subtotal — Equipment Rentals | 2035 | 87.71% | 1785
Misc Labor
Misc Labor Expenses | 3250 | 85% | 2762.5 | General contractor (self-perform)
Subtotal — Misc Labor | 3250 | 85% | 2762.5
Mortgage Principle/Interest
Admin | 1200 | 100% | 1200
Subtotal — Mortgage Principle/Interest | 1200 | 100% | 1200
TOTAL — Building A | 459646 | 49.9% | 229367.5

## Budget — Building B
Construction Budget — Building B
Larger building. Trade-package budget including embedded construction-period interest and management. Progress shown at the reporting date.
Cost centre / scope item | Budget ($) | % complete | Committed to date ($) | Trade / procurement role
Contingency
Contingency | 218500 | 0% | 0
Subtotal — Contingency | 218500 | 0% | 0
Architectural Design
Architectural Design | 6500 | 100% | 6500 | Architectural drafting
Subtotal — Architectural Design | 6500 | 100% | 6500
Architectural Drawings
Architectural Drawings | 4000 | 100% | 4000 | Architect (code)
Subtotal — Architectural Drawings | 4000 | 100% | 4000
Structural Drawings
Structural Drawings | 2400 | 100% | 2400 | Structural engineer
Subtotal — Structural Drawings | 2400 | 100% | 2400
Demolition
Demolition Internal | 8000 | 100% | 8000 | General contractor (self-perform)
Demolition Back section | 5000 | 100% | 5000 | General contractor (self-perform)
Demolition of roof section | 2000 | 100% | 2000 | General contractor (self-perform)
Disposal Costs | 20000 | 85% | 17000 | Waste disposal
Subtotal — Demolition | 35000 | 91.43% | 32000
Electrical Layout
Electrical layout | 400 |  | 0
Subtotal — Electrical Layout | 400 | 0% | 0
Management
PM %4 | 79000 | 65% | 51350 | General contractor (self-perform)
SS %4 | 79000 | 65% | 51350 | General contractor (self-perform)
Carpentry labour | 10000 | 100% | 10000 | General contractor (self-perform)
Company Overhead | 75000 | 65% | 48750 | General contractor (self-perform)
Parking Tickets | 250 | 100% | 250 | Municipality
Interest Estimate | 449666.35 | 70% | 314766.445
Subtotal — Management | 692916.35 | 68.76% | 476466.445
Roofing
Roof OSB | 2400 | 100% | 2400 | Roofing subcontractor
Roofing | 33000 | 100% | 33000 | Roofing subcontractor
Roofing Inspection | 500 | 100% | 500 | Roofing subcontractor
Subtotal — Roofing | 35900 | 100% | 35900
ESA Phase 2 %50
ESA Phase 2 %50 | 8500 | 100% | 8500 | Geotechnical / environmental engineer
Subtotal — ESA Phase 2 %50 | 8500 | 100% | 8500
Vacating Units
Management Overhead | 3500 | 100% | 3500 | Property management / tenant relations
Lock Change | 300 | 100% | 300 | Property management / tenant relations
Vacating Units Payments | 6000 | 100% | 6000 | Property management / tenant relations
Subtotal — Vacating Units | 9800 | 100% | 9800
Networking
Networking Cameras | 2500 | 100% | 2500 | Low-voltage / data subcontractor
Networking Internet | 2800 | 50% | 1400 | Low-voltage / data subcontractor
Subtotal — Networking | 5300 | 73.58% | 3900
Structural Framing
Structural Framing Material | 55000 | 100% | 55000 | Framing material / supply
Structural Framing Labour (incl. carpentry) | 4200 | 100% | 4200 | General contractor (self-perform)
Basement Work for LVLs | 2000 | 100% | 2000 | Framing material / supply
Steel Beams | 4000 | 100% | 4000
Stairs in Back Material | 35000 | 50% | 17500 | Framing material / supply
Material For lumber in stairs | 10000 | 100% | 10000 | Framing material / supply
Framing Stairs Back Labour | 8000 | 0% | 0 | General contractor (self-perform)
Piles | 6000 | 0% | 0 | Helical-pile subcontractor
MISC for stairs | 1500 | 100% | 1500 | General contractor (self-perform)
Subfloor | 10500 | 100% | 10500 | General contractor (self-perform)
Partition Wall Framing | 6000 | 100% | 6000 | General contractor (self-perform)
Temporary Walls | 6500 | 100% | 6500 | General contractor (self-perform)
Roof Truss Fixes (probably) | 1000 | 100% | 1000 | General contractor (self-perform)
Foundation Fix for the horizontal LVL into foundation | 1200 | 0% | 0 | General contractor (self-perform)
Subtotal — Structural Framing | 150900 | 78.33% | 118200
Plumbing
Plumbing Demolition | 2000 | 100% | 2000 | Plumbing subcontractor
Plumbing Rough IN | 16000 | 100% | 16000 | Plumbing subcontractor
Plumbing Finishing | 16000 | 0% | 0 | Plumbing subcontractor
Plumbing Selections | 15000 | 0% | 0 | Plumbing subcontractor
Hot water per unit | 6000 | 0% | 0 | Plumbing subcontractor
Plumbing Extra | 15000 | 50% | 7500 | Plumbing subcontractor
Subtotal — Plumbing | 70000 | 36.43% | 25500
Electrical
Electrical Rough in | 35000 | 70% | 24500 | Electrical subcontractor
Electrical FInishing | 35000 | 0% | 0 | Electrical subcontractor
Electrical Selections | 7000 | 0% | 0 | Electrical subcontractor
Exterior lighting budget | 2500 | 0% | 0 | Electrical subcontractor
Fire Alarm extra | 25500 | 100% | 25500 | Electrical subcontractor
Electrical Extra | 17000 | 50% | 8500 | Electrical subcontractor
Subtotal — Electrical | 122000 | 47.95% | 58500
Flooring
Vinyl Flooring | 35000 | 0% | 0 | Flooring / tile subcontractor
Stairs | 4700 | 0% | 0 | Flooring / tile subcontractor
Transitions | 5000 | 0% | 0 | Flooring / tile subcontractor
Sanding joints and prep extra | 7500 | 0% | 0 | Flooring / tile subcontractor
Subtotal — Flooring | 52200 | 0% | 0
Trim + Moulding
Tim + Mouldings | 28000 | 0% | 0 | Trim & door installer
Installation | 11000 | 0% | 0 | Trim & door installer
Subtotal — Trim + Moulding | 39000 | 0% | 0
Kitchens
Kitchen Cabinets | 80000 | 0% | 0 | Cabinetry supplier
Countertops | 25000 | 0% | 0 | Countertop supplier
Cabinetry schedule allowance | 6000 | 0% | 0 | Cabinetry supplier
Subtotal — Kitchens | 111000 | 0% | 0
Tiles
Tiles Labour | 25000 | 0% | 0 | Flooring / tile subcontractor
Tiles Material | 20000 | 0% | 0 | Flooring / tile subcontractor
Subtotal — Tiles | 45000 | 0% | 0
Remedial Excavation
Earthworks | 2000 | 100% | 2000 | Sitework subcontractor
Engineering | 4500 | 100% | 4500 | Geotechnical / environmental engineer
Waste Disposal | 2000 | 100% | 2000 | Waste disposal
Power washing exterior | 8900 | 0% | 0
Subtotal — Remedial Excavation | 17400 | 48.85% | 8500
Painting
Primer | 2000 | 0% | 0 | Painting subcontractor
Prime Check | 1000 | 0% | 0 | Painting subcontractor
2 Coats | 11000 | 0% | 0 | Painting subcontractor
Touch ups | 1000 | 0% | 0 | Painting subcontractor
Painting xtra | 4000 | 0% | 0 | Painting subcontractor
Subtotal — Painting | 19000 | 0% | 0
HVAC
HVAC Rough in | 15000 | 50% | 7500 | HVAC subcontractor
HVAC Install | 15000 | 0% | 0 | HVAC subcontractor
HVAC Fixes | 6000 | 0% | 0 | HVAC subcontractor
Extras Unforseen | 4000 | 0% | 0 | HVAC subcontractor
Subtotal — HVAC | 40000 | 18.75% | 7500
Insulation
Insulation | 35000 | 0% | 0 | Insulation subcontractor
Basement Sprayfoam | 2000 | 0% | 0 | Insulation subcontractor
Subtotal — Insulation | 37000 | 0% | 0
Windows
Windows | 42000 | 0% | 0 | Window & door supplier
Window Installation | 5000 | 0% | 0 | Window & door supplier
Window Cauking | 1000 | 0% | 0 | Window & door supplier
Subtotal — Windows | 48000 | 0% | 0
Concrete Footing In basement
Concrete footings in basement | 2500 | 50% | 1250 | Concrete subcontractor
Redjack costs | 2500 | 0% | 0
Subtotal — Concrete Footing In basement | 5000 | 25% | 1250
Cleaning
Final Cleaning | 5000 | 0% | 0
Construction Cleaning Internal | 1000 | 0% | 0
Subtotal — Cleaning | 6000 | 0% | 0
Furniture
Assuming budget of 2k per unit | 20000 | 0% | 0
Furniture Labor and installation | 4000 | 0% | 0
TVs | 4000 | 0% | 0
TV mounts | 700 | 0% | 0
Appliances | 40000 | 0% | 0 | Appliance supplier
Subtotal — Furniture | 68700 | 0% | 0
Paving/Landscaping
Front Hardscaping section+Rear | 3500 | 0% | 0 | Sitework subcontractor
Paving Side plus rear | 8500 | 0% | 0 | Paving subcontractor
General grading & sitework | 2000 | 0% | 0 | Sitework subcontractor
Planters | 1500 | 0% | 0
New electrical housing for meters in exterior | 500 | 0% | 0 | General contractor (self-perform)
Subtotal — Paving/Landscaping | 16000 | 0% | 0
Drywall+Plaster
Drywall | 40000 | 0% | 0 | General contractor (self-perform)
Plaster | 25000 | 0% | 0 | Plaster subcontractor
tapping | 10000 | 0% | 0 | Plaster subcontractor
Subtotal — Drywall+Plaster | 75000 | 0% | 0
Signage
Building signage | 2000 | 0% | 0
Subtotal — Signage | 2000 | 0% | 0
Backside Siding
Siding for back and Fascia | 3000 | 0% | 0
Subtotal — Backside Siding | 3000 | 0% | 0
Sound Insulation
Sounds Insulation ceiling material+installation | 20000 | 40% | 8000 | Insulation subcontractor
Subtotal — Sound Insulation | 20000 | 40% | 8000
Parging
Parging | 4500 | 0% | 0 | Parging subcontractor
Subtotal — Parging | 4500 | 0% | 0
Hydro Room Extra
Design | 6500 |  | 0
Concrete | 16682.72 |  | 0
Water Service Upgrade | 18000 |  | 0
Hydro Room | 15000 |  | 0
Subtotal — Hydro Room Extra | 56182.72 | 0% | 0
Builder's Insurance
Builder's Insurance | 11400 | 85% | 9690 | Insurance broker
Subtotal — Builder's Insurance | 11400 | 85% | 9690
TOTAL — Building B | 2038499.07 | 40.06% | 816606.445

## Stabilised Income Pro Forma
Stabilised Income Pro Forma
Year-one stabilised operations. Residential and commercial components underwritten separately, consistent with CMHC MLI Select mixed-use treatment.
RESIDENTIAL INCOME
Component | Basis | Annual ($) | Note
One-bedroom suites | 8 × $1,900/mo | 182400
Three-bedroom suites | 2 × $3,000/mo | 72000
Storage income | $100/mo | 1200
Gross potential revenue — residential |  | 255600
Less: vacancy allowance | 3.00% of GPR | -7668
Effective gross revenue — residential |  | 247932
RESIDENTIAL OPERATING EXPENSES
Component | % of EGR | Annual ($) | Basis
Property taxes | 8.067% | 20000 | 2024 final tax bill
Insurance | 1.815% | 4500 | 2024 insurance bill
Utilities | 5.243% | 13000 | ICI estimate
Repairs and maintenance | 3.348% | 8300 | CMHC Ontario benchmark
Replacement reserve | 1.21% | 3000 | CMHC benchmark, $60/appliance
Salaries | 2.239% | 5550 | CMHC Ontario benchmark
Management fee | 4.25% | 10537.11 | 4.25% of EGR — CMHC benchmark
Other costs | 1% | 2479.32 | 1.00% of EGR — CMHC benchmark
Total operating expenses | 27.17% | 67366.43
Net operating income — residential |  | 180565.57
COMMERCIAL COMPONENT (GROUND-FLOOR RETAIL)
Component | Basis | Annual ($) | Note
Gross potential revenue — retail | 730 SF @ $65.75/SF | 48000
Less: vacancy allowance | 5.00% | -2400
Effective gross revenue — retail |  | 45600
Less: operating cost | $3.39/SF | 2474
Net operating income — commercial |  | 43126
NET OPERATING INCOME — TOTAL |  | 223691.57
Underwriting rounds total NOI to $223,691; formula result differs by ~$1 from rounding in the source operating-expense lines.

## CMHC MLI Select Financing
CMHC MLI Select Financing
Construction-to-takeout under the CMHC MLI Select mixed-use stream. Each tranche is sized by its binding constraint — the residential tranche by debt-service coverage, the commercial tranche by loan-to-value.
TAKEOUT DEBT SIZING
Tranche | Loan ($) | Rate | Annual debt service ($) | DSCR
First mortgage — residential | 3337488 | 3.9% | 164128 | 1.1002
First mortgage — commercial | 498000 | 3.9% | 24490 | 1.761
Total / blended | 3835488 |  | 188618 | 1.186
COVERAGE & CASH FLOW
Stabilised net operating income |  |  | 223691.57
Less: total annual debt service |  |  | -188618
Cash flow after debt service |  |  | 35073.57
Blended debt-service coverage |  |  | 1.186
Amortisation / term |  |  | 40 yr / 5 yr
SIZING LOGIC
• The residential tranche binds on the 1.10x DSCR floor: maximum debt service equals residential NOI divided by 1.10, which sets the loan near its 92.4% loan-to-value ceiling.
• The commercial tranche binds on the 75% loan-to-value limit; its 1.76x coverage sits well above the floor.
• Blended coverage of 1.19x leaves roughly $35,073 of annual cash flow after debt service — thin, and sensitive to rent and rate movement.

## Returns & Valuation
Returns & Valuation
Derived analysis. The capitalised value, yield on cost, development margin, and equity-recovery metrics below are computed from the cost, income, and financing tabs. A sponsor view follows the market view.
PROJECT COST
Construction — Building A |  | 459646
Construction — Building B |  | 2038499.07
Land acquisition (APS) |  | 1700000
Total project cost |  | 4198145.07
Committed to date |  | 2745973.945
Per cent of budget committed |  | 65.41%
INCOME & CAPITALISED VALUE
Stabilised net operating income |  | 223691.57
CMHC implied lending value — residential |  | 3612000
CMHC implied lending value — commercial |  | 664000
CMHC implied lending value — total |  | 4276000
Implied going-in cap rate (NOI / lending value) |  | 5.231%
Stabilised value at going-in cap rate |  | 4260791.8095
RETURN METRICS — MARKET BASIS
Yield on cost (NOI / total project cost) |  | 5.328%
Development spread (yield on cost − cap rate) |  | 0.07834%
Development profit (value − cost) |  | 62646.7395
Development margin on cost |  | 1.492%
Takeout debt (total) |  | 3835488
Equity remaining at takeout (cost − debt) |  | 362657.07
Debt as per cent of cost |  | 91.36%
Cash-on-cash on remaining equity |  | 9.671%
SPONSOR ECONOMICS — MANAGEMENT FEES RETAINED AS PROFIT
Management, supervision & overhead fees retained by sponsor |  | 340000
Development profit, market basis (value − cost) |  | 62646.7395
Total sponsor profit (market profit + retained fees) |  | 402646.7395
Total sponsor profit margin on total cost |  | 9.591%
Total sponsor profit margin on third-party cost |  | 10.44%
The fees above were paid to the developer, which is the project sponsor; in a sponsor's hands they are retained margin, not a third-party cost. The construction budget's explicit management, supervision, and corporate-overhead lines total about $283,200; the retained figure of $340,000 also captures margin on self-performed scope. Corporate overhead is modest because it is spread across a portfolio of concurrent projects. An arm's-length buyer or lender treats these fees as real costs — the market-basis profit above stands for valuation; the sponsor view stands for the developer's own return.
SENSITIVITY — CAPITALISED VALUE & PROFIT vs EXIT CAP RATE
Exit capitalisation rate | 4.75% | 5% | 5.25% | 5.5% | 5.75%
Capitalised value | 4709296.2105 | 4473831.4 | 4260791.8095 | 4067119.4545 | 3890288.1739
Development profit, market basis (value − cost) | 511151.1405 | 275686.33 | 62646.7395 | -131025.6155 | -307856.8961
Total sponsor profit (incl. retained fees) | 851151.1405 | 615686.33 | 402646.7395 | 208974.3845 | 32143.1039
READING
On a market basis the development margin on cost is thin at the implied entry cap rate, and value is created mainly by the takeout structure: high-leverage, low-rate, forty-year CMHC debt recovers roughly 91 per cent of cost, leaving a small equity balance at a strong cash yield. On a sponsor basis the picture is materially better, because about $340,000 of what the budget books as management, supervision, and overhead is paid to the developer and retained as profit; counting it lifts total sponsor profit toward $400,000 and the margin on cost to roughly nine to ten per cent. A 25-basis-point move in the exit cap rate still swings value by more than $200,000 under either view.

## Risk & Sensitivity
Risk & Sensitivity
Expected-value risk register. Likelihood and impact are management estimates; expected cost is their product. The expected-value total is compared with the contingency carried in the construction budgets.
ID | Risk | Likelihood | Impact ($) | Expected ($) | Mitigation
R-1 | MLI Select scoring shortfall reduces takeout leverage | 25% | 250000 | 62500 | Engage CMHC pre-application; hold equity cushion.
R-2 | Takeout rate exceeds the 3.90% modelled at stabilisation | 30% | 90000 | 27000 | Negotiate rate hold at commitment; stress the coverage.
R-3 | Residential lease-up slower than the 3% vacancy assumption | 30% | 60000 | 18000 | Pre-marketing; staged occupancy; reserve.
R-4 | Single retail tenancy stays vacant on completion | 30% | 48000 | 14400 | Early leasing; underwrite to a conservative retail rent.
R-5 | Construction cost overrun beyond the contingency carried | 30% | 150000 | 45000 | Fixed-price subcontracts on major trades; draw monitoring.
R-6 | Exit or refinance cap rate expands above the going-in rate | 40% | 210000 | 84000 | Hold strategy reduces forced-sale exposure; monitor spreads.
R-7 | HST self-supply or rebate treatment on the mixed-use complex | 35% | 109000 | 38150 | Tax counsel on PBRH versus NRRP eligibility before occupancy.
R-8 | Contamination or hazardous material found in demolition | 30% | 40000 | 12000 | ESA Phase 2 underway; abatement allowance in budget.
R-9 | Schedule slippage extends construction-period interest | 35% | 55000 | 19250 | Critical-path management; lender-monitored draws.
R-10 | Adjacent-property or party-wall damage (infill site) | 15% | 75000 | 11250 | Builder's risk with party-wall extension; pre-condition survey.
| Expected-value risk budget |  |  | 331550
COVERAGE
| Contingency reserve carried in budgets |  |  | 248500 | Building A $30,000 minor + Building B $218,500.
| Coverage of expected-value risk |  |  | -83050 | Positive means the carried contingency exceeds expected risk.
SENSITIVITY POINTERS
• Cash flow after debt service ($35,073) is the thinnest line in the model; a 50-basis-point rise in the takeout rate or a sustained 5% rent shortfall erodes most of it.
• The Returns & Valuation tab grids capitalised value and development profit across a ±50-basis-point cap-rate band.
• The single largest discrete exposure is the HST treatment of the mixed-use complex (R-7), worth roughly $109,000 depending on rebate eligibility.

## Sources & Method
Sources & Method
Authorities relied on, the basis of the numbers, and the anonymisation applied to this sample.
SOURCES & AUTHORITIES
Domain | Citation
Mortgage insurance | CMHC MLI Select Program — multi-unit residential and mixed-use; Tier-based energy and affordability incentives.
Rental market | CMHC Rental Market Report, Ottawa CMA — submarket vacancy benchmarks (four-year average near 2.63%).
Operating benchmarks | CMHC Ontario operating-cost benchmarks — repairs, replacement reserve, salaries, management and other costs.
HST self-supply | Excise Tax Act, R.S.C. 1985, c. E-15, s. 191(3); CRA Guide RC4231 — self-supply on substantial completion of a residential complex.
HST rebates | Excise Tax Act s. 256.2 (New Residential Rental Property) and s. 256.2.1 (Purpose-Built Rental Housing); CRA Guide 19-3-9 — mixed-use eligibility.
Land transfer tax | Land Transfer Tax Act, R.S.O. 1990, c. L.6, s. 2(1).
Development charges | City of Ottawa Development Charges By-law, as amended; Development Charges Act, 1997, s. 2(3.2) (additional-unit exemptions).
Cost estimating | AACE International Recommended Practice 18R-97 — Cost Estimate Classification System.
Risk method | Project Management Institute, Construction Extension to the PMBOK Guide, 2022 — expected-value risk treatment.
Privacy | Personal Information Protection and Electronic Documents Act, S.C. 2000, c. 5 — basis for anonymisation.
METHODOLOGY & RECONCILIATION
• Total project cost ties exactly to source: Building A $459,646 + Building B $2,038,499 + land $1,700,000 = $4,198,145. Committed-to-date of $2,745,974 (65.4% overall; 41.9% of construction) reconciles to the source progress columns.
• Building B carries embedded construction-period interest of about $449,666; this is the construction loan's cost, separate from the CMHC takeout debt service modelled on the financing tab.
• The income pro forma reproduces the underwriting as given; the formula total of net operating income differs from the underwriting's $223,691 by about one dollar, from rounding in the source operating-expense lines.
• Loan tranches are sized by the binding constraint: the residential tranche by the 1.10x DSCR floor, the commercial tranche by the 75% loan-to-value limit.
• Capitalised value, yield on cost, development margin, and equity-recovery figures are derived by Lumenalis from the cost, income, and financing inputs; they are analysis, not an appraisal.
• The construction budget is organised by trade package, not by cost class. The Hard / Soft / Management / Financing / Contingency split, where referenced, is an analytical overlay on the same line items and reconciles to the construction subtotal.
ANONYMISATION (PIPEDA)
The street address, postal code, the developer, all vendor and subcontractor names, and repository links have been removed and replaced with the project codename, a generic location, and generic trade roles. All monetary figures are retained, since the figures are the instructive content of the sample. This treatment follows the Personal Information Protection and Electronic Documents Act, S.C. 2000, c. 5.
Note on presentation: bold weight is deprecated in the Lumenalis brand. Section bands, column headers, and total rows use background fill and the display typeface for structure instead. In a dense financial spreadsheet this is a deliberate, functional deviation that preserves legibility without bold body text.