## Cover
ENGAGEMENT REPORT · REAL ESTATE DEVELOPMENT ADVISORY
Single-Family Renovation & Resale
Pro-Forma Budget & Investment Return Analysis
Anonymised case study · suburban Ottawa, Ontario
Prepared by Lumenalis Consulting Ltd.
SUBJECT PROPERTY PROFILE
Asset type | Detached single-family dwelling
Location | Suburban Ottawa, Ontario (address withheld)
Approx. year built | 1985
Approx. gross floor area | 1,750 sq ft
Approx. lot size | 7,700 sq ft
Configuration | 5 bedrooms · 2 bathrooms · 2-car garage
Business plan | Acquire, renovate and resell within an approx. 12-month hold
HEADLINE OUTPUTS
Purchase price |  | 610000
Renovation budget — hard, soft & contingency (itemised) |  | 125193
All-in project cost — deal pro-forma |  | 804319
Gross resale price |  | 900000
Net sale proceeds |  | 882000
Net profit to equity |  | 86848
Return on invested equity |  | 32.51%
Equity multiple |  | 1.3251
Levered IRR — annualised (source-reported) |  | 50.34%
Document control no. | LUM-RP-RES01-01.00
Version / date | v1.0 · 2026-05-21
Prepared for illustration. Monetary values are those from the underlying engagement; property address, postal code, ownership and document links have been removed for publication under PIPEDA (S.C. 2000, c.5). See Sources & Method for the anonymisation note, the two-basis cost reconciliation, and methodology.

## Summary
Pro-Forma Summary
Single-family acquisition, renovation and resale — deal pro-forma
SOURCES OF CAPITAL |  |  |  | USES OF CAPITAL
Source |  | Amount | % of total | Use | Amount
Senior mortgage loan |  | 537160 | 66.78% | Purchase price + acquisition closing | 616100
Secondary financing (mezzanine / hard money) |  | 0 | 0% | Loan arrangement fees | 5372
Sponsor equity |  | 0 | 0% | Loan payments during hold | 31446
Investor equity |  | 267159 | 33.22% | Renovation / construction draw (modelled) | 151401
TOTAL SOURCES |  |  |  | TOTAL USES
Sources = Uses (balance check)
DISPOSITION WATERFALL |  |  |  | RETURN METRICS
Line |  | Amount
Gross resale price |  | 900000 |  | Net profit to equity | 86848
Less: sale closing costs (2.0%) |  | -18000 |  | Return on invested equity | 32.51%
Net sale proceeds |  | 882000 |  | Equity multiple | 1.3251
Less: senior mortgage payoff |  | -527993 |  | Levered IRR — annualised (source-reported) | 50.34%
Equity distribution |  | 354007 |  | Hold period | 1
Less: investor equity contributed |  | -267159
NET PROFIT TO EQUITY |  | 86848
PARTNERSHIP SPLIT
Party | Contributed | Distributed | Net profit
Sponsor | 0 | 0 | 0
Investor | 267159 | 354007 | 86848
Two cost bases appear in the source model and are preserved here without forcing a false reconciliation: the granular cost tracker (see Hard Costs, Soft Costs, Contingency, Financing & Holding) totals approximately $773,514 all-in excluding mortgage principal, while the deal pro-forma above models a $151,401 construction draw and $31,446 of loan payments, totalling $804,319 of uses. The authoritative investment outcome (net profit, equity multiple, IRR) is taken from the deal-level weekly cash-flow model. The two bases differ chiefly in interest treatment and the construction-draw assumption.

## Assumptions
Assumptions & Inputs
Values shown are the engagement inputs. Edit an input and the dependent sheets recompute.
PROGRAM & TIMING
Input | Value | Basis / note
Hold period (weeks) | 52 | Acquisition to resale; approx. 12 months.
Renovation window |  | Weeks 8–40 of the hold.
Default area unit | sq ft | Imperial, per source.
ACQUISITION
Input | Value | Basis / note
Purchase price | 610000 | Negotiated acquisition price.
Deposit (within purchase price) | 90000 | Paid at agreement; not additive to purchase.
Acquisition closing costs | 6100 | Legal, land transfer tax, disbursements (single source line — see Acquisition sheet note).
RENOVATION
Input | Value | Basis / note
Renovation — hard costs | 86633 | Itemised across six trade divisions; see Hard Costs.
Renovation — soft costs | 24660 | Design, permitting, administration, disposition; see Soft Costs.
Construction contingency | 11900 | AACE 18R-97 class band on hard costs.
Design contingency | 2000 | On soft costs.
FINANCING
Input | Value | Basis / note
Senior mortgage advance | 537160 | Construction / acquisition facility.
Senior interest rate (annual) | 4.18% | Fixed; amortising (not interest-only).
Amortisation |  | 30-year amortisation; payoff at resale (week 52).
Loan arrangement fees | 5372 | Charged at facility start.
Senior mortgage payoff at sale | 527993 | Outstanding balance discharged from sale proceeds.
Secondary financing | 0 | Not used in this scenario.
Sponsor equity | 0 | Not used in this scenario.
Investor equity | 267159 | Balancing equity contribution.
HOLDING
Input | Value | Basis / note
Property taxes (hold period) | 4400 | Municipal taxes over the hold.
Property insurance |  | Course-of-construction / vacancy cover; nominal in source.
DISPOSITION
Input | Value | Basis / note
Gross resale price | 900000 | Post-renovation market value assumption.
Sale closing costs | 2% | Commission / legal / disbursements as % of resale (= $18,000).

## Acquisition & Closing
Acquisition & Closing
ACQUISITION COST BASE
Item | Amount | Basis / note
Purchase price | 610000 | Negotiated price for the subject dwelling.
of which: deposit at agreement | 90000 | Memo line — included in the purchase price above, not additive.
Acquisition closing costs | 6100 | Legal fees, land transfer tax and disbursements recorded as a single line.
TOTAL ACQUISITION COST |  | Excludes deposit memo line.
Land transfer tax check (analytical overlay, not a restatement): Ontario LTT on a $610,000 conveyance is approximately $8,675 under the marginal brackets of the Land Transfer Tax Act, R.S.O. 1990, c. L.6, s. 2(1) — 0.5% to $55,000, 1.0% to $250,000, 1.5% to $400,000, 2.0% above. Ottawa levies no municipal land transfer tax. The single $6,100 closing line therefore appears to exclude or understate statutory LTT; the cost base should be verified before reliance. This mirrors the land-transfer-tax adjustment applied in the comparable ground-up engagement.

## Hard Costs
Renovation — Hard Costs
Cost item | Budget | Actual | Variance | % comp. | Cost to complete
Site Preparation & Demolition
Full demolition of structural components | 2250 | 2250
Hazardous-materials abatement (asbestos, lead, mould) | 25 | 25
Site clearing & waste disposal | 0 | 0
Temporary protection & hoarding | 500 | 0
Subtotal — Site Preparation & Demolition
Structural & Building Envelope
Structural framing reinforcement / replacement | 750 | 0
Foundations & underpinning | 0 | 0
Masonry repair & repointing | 0 | 0
Roofing repair / replacement | 8000 | 0
Exterior wall cladding | 350 | 0
Window & door replacements | 9850 | 0
Subtotal — Structural & Building Envelope
Interior Construction
Interior framing & drywall | 15632.5 | 0
Painting & wall finishes | 6500 | 0
Flooring (tile, hardwood, vinyl) | 4800 | 0
Ceiling systems | 0 | 0
Trim | 1500 | 0
Stairs, railings, balustrades | 2500 | 0
Subtotal — Interior Construction
Mechanical, Electrical & Plumbing
HVAC systems (replacement / upgrade) | 4500 | 0
Plumbing fixtures & piping | 9725 | 350
Electrical service upgrades & rewiring | 4000 | 0
Lighting fixtures & controls | 1000 | 0
Fire alarm & suppression | 250 | 0
Data, communications & security | 200 | 50
Subtotal — Mechanical, Electrical & Plumbing
Fixtures, Fittings, Equipment & Insulation
Kitchen cabinetry & countertops | 5600 | 1440
Insulation | 4200 | 0
Mirrors & accessories | 1000 | 0
Appliances | 3500 | 0
Window coverings | 0 | 0
Built-in furniture | 0 | 0
Subtotal — Fixtures, Fittings, Equipment & Insulation
TOTAL
Hard-cost line items as scoped in the engagement. Budget is the initial estimate; Actual is recorded spend to the reporting date. The 1985 vintage of the dwelling is the reason a designated-substances (asbestos / lead) abatement line is carried — see Risk & Sensitivity and Sources & Method.

## Soft Costs
Renovation — Soft Costs
Cost item | Budget | Actual | Variance | % comp. | Cost to complete
Professional & Design Services
Architectural & interior design fees | 1000 | 0
Structural / mechanical / electrical engineering | 0 | 0
Quantity surveying / cost consulting | 0 | 0
Building-envelope consultants | 0 | 0
Specialty consultants (acoustics, heritage, lighting) | 2500 | 0
Subtotal — Professional & Design Services
Permitting & Approvals
Building permit fees | 500 | 0
Development charges (if applicable) | 4100 | 0
Heritage approvals | 0 | 0
Utility connection fees | 500 | 0
Subtotal — Permitting & Approvals
Project Administration
Project management fees (internal or external) | 13000 | 2300
Site supervision (clerk of works) | 0 | 0
Legal fees for contracts & disputes | 0 | 0
Insurance (builder's risk, general liability) | 2160 | 180
Subtotal — Project Administration
Disposition & Marketing
Marketing & sale prep (staging, photography, advertising) | 500 | 0
Moving / clear-out costs | 400 | 0
Subtotal — Disposition & Marketing
TOTAL
Soft costs cover design, approvals, project administration and disposition. Development charges are carried as a contingent line; most renovations of an existing single dwelling do not trigger them, but the allowance is retained pending confirmation of scope.

## Contingency
Contingency
Cost item | Budget | Actual | Variance | % comp. | Cost to complete
Contingency
Construction contingency (on hard costs) | 11900 | 0
Design contingency (on soft costs) | 2000 | 0
Escalation allowance (inflation over the build) | 0 | 0
Unforeseen-conditions allowance (existing-building unknowns) | 0 | 0
Subtotal — Contingency
TOTAL
Contingency is decomposed by risk category after AACE International Recommended Practice 18R-97. The construction contingency of $11,900 is approximately 14% of itemised hard costs — defensible for a renovation of a 40-year-old dwelling where concealed conditions are likely.

## Financing & Holding
Financing & Holding Costs
Cost item | Budget | Actual | Variance | % comp. | Cost to complete
Financing Costs
Loan arrangement fees | 5371.6 | 5371.6
Interest during renovation (senior facility) | 9350 | 779.17
Appraisal fees | 1500 | 750
Legal closing costs (financing) | 11600 | 11600
Loan origination fees | 0 | 0
Lender's cost-consultant fees | 0 | 0
Title insurance | 0 | 0
Subtotal — Financing Costs
Holding Costs
Property taxes (hold period) | 4400 | 2200
Property insurance (course-of-construction) | 0 | 0
Subtotal — Holding Costs
TOTAL
SENIOR FACILITY — TERMS & FLOWS
Senior mortgage advance | 537160
Annual interest rate (fixed) | 4.18%
Amortisation | 30-yr (not interest-only)
Indicative monthly payment | 2620.54
Payoff at resale (week 52) | 527993
Interest during renovation ($9,350 budgeted) is the carry over the active build window; the deal-level cash-flow model instead books total loan payments of $31,446 across the full 52-week hold, which is why the two cost bases differ. The senior facility is discharged from sale proceeds at resale.

## Returns & Investor
Returns & Investor Analysis
DISPOSITION WATERFALL |  |  |  | RETURN METRICS
Gross resale price |  | 900000 |  | Net profit to equity
Less: sale closing costs (2.0%) |  |  |  | Equity multiple
Net sale proceeds |  |  |  | Return on invested equity
Less: senior mortgage payoff |  | -527993 |  | Levered IRR — annualised (source-reported) | 50.34%
Equity distribution |  |  |  | Hold period | 1
Less: investor equity contributed |  | -267159
NET PROFIT TO EQUITY
PARTNERSHIP DISTRIBUTION
Party | Contributed | Distributed | Net profit
Sponsor | 0 | 0 | 0
Investor | 267159 | 354007 | 86848
Equity multiple = equity distribution ÷ equity contributed. Return on invested equity = net profit ÷ equity contributed. The levered IRR (50.3%, annualised) is taken from the source's weekly cash-flow model and is reported here rather than recomputed. In this scenario the sponsor co-invests no equity, so the modelled profit accrues to the investor; any sponsor promote or fee split would be layered on top and is out of scope for this sample.

## Risk & Sensitivity
Risk & Sensitivity
NET-PROFIT SENSITIVITY — RESALE PRICE × RENOVATION OVERRUN
Net profit to equity ($). Rows = resale price; columns = renovation cost vs. budget.
Resale \ Reno | -10% | Budget | +10% | +25%
850000 | 50367 | 37848 | 25329 | 6550
875000 | 74867 | 62348 | 49829 | 31050
900000 | 99367 | 86848 | 74329 | 55550
925000 | 123867 | 111348 | 98829 | 80050
950000 | 148367 | 135848 | 123329 | 104550
Computed from the deal's own figures (net sale = resale × 0.98; senior payoff $527,993 fixed; renovation overrun adds dollar-for-dollar to required investor equity because the debt is fixed). Base case is shaded. The single largest driver of outcome is the resale assumption: a $50,000 swing in resale moves net profit by roughly $49,000, materially more than a 25% renovation overrun (~$31,000).
RISK REGISTER (ILLUSTRATIVE — LUMENALIS METHODOLOGY OVERLAY)
Risk | Primary driver |  | Exposure |  | Mitigation
Resale-price softening | Ottawa resale market at disposition |  | Highest single sensitivity | List early; price to comparable evidence; hold-period flexibility.
Renovation cost overrun | Concealed conditions in a 1985 dwelling |  | Adds dollar-for-dollar to equity | Pre-purchase inspection; designated-substances survey; 14% construction contingency.
Schedule slippage | Trade availability; permit timing |  | Extends interest & tax carry | Critical-path sequencing; lock subcontractor scopes; weekly tracking.
Interest / carry | Senior facility cost over the hold |  | Erodes net profit | Fixed-rate facility; minimise hold; staged draws.
Disposition liquidity | Buyer demand at the price point |  | Delays payoff; raises carry | Pre-market the asset; staging budget retained.
Permitting / compliance | Building-permit and inspection regime |  | Delay and rework risk | Confirm scope-of-work permits early; engage trades with inspection track record.
The register is an analytical overlay applying Lumenalis methodology; likelihood and dollar-impact scoring are deliberately omitted because they were not part of the client engagement and would be fabricated if asserted here.

## Document Register
Document Register
Standard document checklist maintained for the engagement. Repository links removed for publication.
Category | Document | Status / note
Admin | Project document repository | [ project drive — link redacted for publication ]
Acquisition | Purchase and Sale Agreement (PSA)
Acquisition | Deposit receipt
Acquisition | Title search / title report
Acquisition | Title insurance policy
Acquisition | Property survey
Acquisition | Deed / transfer of title
Acquisition | Property disclosure statement (if applicable)
Financing | Loan commitment letter
Financing | Promissory note
Financing | Mortgage / charge
Financing | Personal guarantee (if required)
Financing | Loan draw schedule
Financing | Appraisal report
Financing | Lender inspection reports
Renovation | Scope of work (SOW)
Renovation | Construction budget
Renovation | General contractor agreement
Renovation | Subcontractor agreements
Renovation | Change-orders log
Renovation | Permits & permit applications
Renovation | Inspection reports (building, electrical, plumbing)
Renovation | Material & fixture specifications
Renovation | Warranties
Renovation | Lien waivers
Insurance | Builder's risk insurance policy
Insurance | General liability insurance policy
Insurance | Workers' compensation certificates
Compliance | Zoning verification letter
Compliance | Environmental reports (Phase I ESA if applicable)
Compliance | Occupancy certificate / final inspection approval
Disposition | Listing agreement
Disposition | Comparative market analysis (CMA)
Disposition | Offer / agreement of purchase & sale
Disposition | Vendor disclosure statement
Disposition | Statement of adjustments
Disposition | Final settlement documents
Project mgmt. | Project schedule / Gantt
Project mgmt. | Weekly progress reports
Project mgmt. | Invoice log
Project mgmt. | Receipts archive
Project mgmt. | Photo documentation (before / during / after)

## Advisory Log
Advisory Time Log
Advisory hours recorded against the engagement. Shown for illustration of scope.
Session | Activity | Hours | Recorded value
Session 1 | Meeting / site visit | 2.25 | 150.75
Session 2 | System work | 1.333 | 89.33
Session 3 | Strategy / calculation | 2.25 | 150.75
Session 4 | Strategy / calculation | 1.25 | 83.75
Session 5 | Strategy / calculation | 0.583 | 39.08
Session 6 | Strategy / calculation | 0.333 | 22.33
Session 7 | Strategy / calculation | 4.5 | 301.5
TOTAL
Recorded value reflects advisory time only and is shown for transparency of engagement scope; it is not a quote of current Lumenalis rates.

## Sources & Method
Sources & Method
ANONYMISATION NOTE
Standard applied | Personal Information Protection and Electronic Documents Act (PIPEDA), S.C. 2000, c. 5. Direct identifiers removed: street address, postal code, ownership, and the project document-repository link. The property profile (vintage, area, configuration) and all monetary figures are retained because, absent the address, they do not identify an individual and they carry the analytical value of the sample.
METHOD & CITATIONS
Cost-classification & contingency | AACE International, Recommended Practice 18R-97 — Cost Estimate Classification System. Used to frame the contingency decomposition.
Land transfer tax | Land Transfer Tax Act, R.S.O. 1990, c. L.6, s. 2(1). Basis for the LTT check on the Acquisition sheet. Ottawa levies no municipal land transfer tax.
Designated substances | O. Reg. 278/05 (Designated Substances — Asbestos) under the Occupational Health and Safety Act. Basis for carrying an abatement allowance on a 1985 dwelling.
Return definitions | Equity multiple = distribution ÷ contribution; return on invested equity = net profit ÷ contribution; levered IRR from the weekly cash-flow model (source-reported, not recomputed here).
Two-basis reconciliation | The granular cost tracker (Hard, Soft, Contingency, Financing & Holding) totals approx. $773,514 all-in excluding mortgage principal. The deal pro-forma (Summary, Returns) models a $151,401 construction draw and $31,446 of loan payments for $804,319 of uses. The bases differ in interest treatment and construction-draw assumption; neither was altered.
Source workbook | Single-family acquisition-renovation-resale model (engagement working file). Tabs not used in the engagement — a bundled generic development template and operating-income modules — were excluded.
BRAND & FORMAT
Standard | Produced to the Lumenalis brand standard v2.0 (Charcoal #3D3D3D, Stone #8C8C8C, White; Montserrat display, Lato body). Spreadsheet weight contrast is a justified functional deviation from the prose 'no-bold' rule, used only on section bands and totals. Saved as .xlsx for lossless import into Google Sheets.